## README
National Energy Compact Progress Report: Nigeria
Last update: DD/MM/YYYY
This workbook is designed to monitor progress toward the reform commitments made by countries under the action plan of the National Energy Compacts. It provides a structured and consolidated monitoring of key policy actions and targets, enabling consistent tracking, data aggregation, and reporting across M300 Compact countries
STRUCTURE OF THE PROGRESS REPORT: ==> Country Worksheets: Each country has two dedicated worksheets: o One for policy actions (including top 10 priority actions), and o One for target monitoring, which covers four thematic areas: Energy Access, Clean Cooking, Renewable Energy Share & Private Capital Mobilization
DATA ENTRY GUIDELINES
POLICY PROGRESS REPORT: o Please do not modify the reference columns (I, L, O, and Q). These are read-only columns reserved for past data (Energy Compact reference expected completion date, Previous Status, Previous Comments, and Note/Guideline for CDMU). If you have any new updates or changes, please type them exclusively in the "New CDMU comment/update" column (column P). o Enter Adjusted Expected completion date by CDMU in the format DD/MMM/YY only. This should only be filled in when the date varies from the "Energy Compact reference expected completion date" column: For example, this applies when the expected completion date in the compact has passed, and the status is 'delayed', or when the action can be completed earlier than planned. o Enter actual completion dates in the format DD/MMM/YY only. This should only be filled in when the action has been completed. o Enter last update dates in the format DD/MMM/YY only. These dates refer to the most recent date for which activity was reported for the policy action (not the date of the completion of the worksheet). o Use the dropdown menu in the Status column (M) to select one of the predefined options for non-priority policy actions: On Track, Delayed, Completed. On Track actions refer to actions for which implementation activities have been initiated but have not been concluded. Delayed actions refer to those actions for which implementation activities have been initiated but face significant bottlenecks that have caused delays, or for which activities have not yet been initiated, but the planned deadline has passed. Completed actions refer to those actions for which implementation activities have been concluded. o For top 10 priority actions, more granular reporting is required. Please select one of the following predefined options as applicable and include exhaustive explanations in the comments column (P): a. Not Yet Due – No Activity Started for the policy action. This status refers to future actions for which no activities have been initiated b. In Progress – On Track: This refers to actions for which implementation activities have been initiated and which are progressing well with no issues; c. In Progress – Minor Delays: This refers to actions for which implementation activities have been set in motion but have faced slight issues or minor delays; d. In Progress – At Risk: This refers to actions for which major challenges have been encountered, and there is a risk of delay; e. Delayed: This refers to actions for which deadlines have been missed, and the activities remain incomplete; f. Completed: This refers to actions for which every implementation activity has been concluded and the action has been finalized. o Please provide a relevant comment for each policy action (in column P). To guide you, previous comments from the last data collection cycle are placed directly next to your input cell: previous CDMU comments are in the column to the left (column O), and SEForAll Guides/Notes are in the column to the right (column Q).
TARGET PROGRESS REPORT: o Electricity Access: Enter either the number of people electrified or the number of connections using the appropriate rows: > Row 4: Use this row if reporting the number of people electrified. > Row 5: Use this row if reporting the number of connections. If you use Row 5, you must also provide the average number of people per household in Row 6 o Clean Cooking Access: Enter as a percentage of the total country population. o Renewable Energy Share: Enter as a percentage of the generation mix. o Private Capital Mobilization: Enter in US$ million.
COMPACT PROGRESS REPORT MANAGEMENT AND UPDATE PROCESS
• RESPONSIBILITY: Government’s Compact Delivery and Monitoring Units (CDMUs) are responsible for updating both the Policy Progress Report and the Target Progress Report twice per year. SEforALL will subsequently analyze the data submitted and generate progress reports based on the data. • REPORTING: SEforALL compiles and shares summary reports on policy and target progress with all partners. A publicly available version may be developed later once agreed with the governments and the M300 partners.
DATA SOURCES: All data must be based on the most recent and verified information provided by the CDMUs to ensure consistency and accuracy across all indicators. The data sources related to the four targets should be clearly stated in the tracker.
Important note: Due to differences in reporting methodologies across countries, target-related progress should not be aggregated or used for direct comparisons.
Should you require any clarification or guidance, please do not hesitate to contact us, keeping the partners in CC.
;

## Nigeria Actions
Country Code | PL Code | SC Code | PA Code | S.NO |  | Action | Priority Action? | Energy Compact Reference Expected completion date | Adjusted Expected Completion date | Actual completion date | Previous Status (2nd Cycle) | Current Status | Last update | Comment from Previous reporting cycle (2nd Cycle) - For reference | New CDMU Comment/Update | SEForALL Comments (2nd Cycle) - Note for CDMU awareness & Action
Pillar I Expand generation and invest into transmission and distribution (T&D) infrastructure at competitive costs
NGA | 1 | 1 | #NAME? | 01 | Integrated least-cost power system planning adopted incorporating regional resources | Finalize and adopt the comprehensive Power System Master Plan (PSMP)/Integrated Resource Plan | No | 2026-07-31 |  |  | On Track |  | DD-MMM-YY | The Transmission Expansion Plan has been developed and will be integrated into the NIRP. |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 02 | Integrated least-cost power system planning adopted incorporating regional resources | States could create their own energy policy in line with the national one. The national regulator should collaborate with State governments to develop an action plan to guide the transfer of responsibilities to State regulators | No | 2027-12-31 |  |  | Delayed |  | DD-MMM-YY | The expectation is for states to create their IRP as the electricity markets are being developed. There have been delays or challenges in the States' developing their IRP. The recommendation is for the M300 to support the development of State IRPs (for States with regulatory autonomy) |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 03 | Integrated least-cost power system planning adopted incorporating regional resources | The regulator institutionalizes arrangements and defines processes for the systematic update of the 5-year horizon least-cost power development plan (LCPDP) | No | 2026-12-31 |  |  | On Track |  | DD-MMM-YY | The NIRP is embedded in NISO (quasi-regulator) with support from NERC. The next steps will include the review of the NIRP to feature current realities in the sector. |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 04 | Integrated least-cost power system planning adopted incorporating regional resources | States should develop and operationalize Integrated Resource Plans (IRPs) or at least conduct realistic demand studies | No | 2027-12-31 |  |  | Delayed |  | DD-MMM-YY | Some states have their IRP, i.e., Lagos, Oyo, and Enugu. M300 to provide structured support for States with regulatory autonomy to develop their IRP |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 05 | Integrated least-cost power system planning adopted incorporating regional resources | The regulator institutionalizes the Integrated Resource Plan as a roadmap to implement the LCPDP with the IRP now ready to guide the sector’s development | No | 2027-12-31 |  |  | On Track |  | DD-MMM-YY | NISO currently operationalising the IRP |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 06 | Integrated least-cost power system planning adopted incorporating regional resources | Demand studies and IRPs should serve as the foundation for procuring generation capacities | No | 2027-12-31 |  |  | Delayed |  | DD-MMM-YY | Demand Studies to be updated |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 07 | Integrated least-cost power system planning adopted incorporating regional resources | Regulator to approve LCPDP – a precursor to the IRP with the IRP already prepared and ready for implementation | No | 2026-12-31 |  |  | On Track |  | DD-MMM-YY | The Transmission Expansion Plan has been developed and will be integrated into the NIRP. |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 08 | Integrated least-cost power system planning adopted incorporating regional resources | NERC Approval of an Action Plan roadmap for unbundling of Transmission Company of Nigeria (TCN) into i) An Independent System Operator (ISO) and ii) Transmission Service Providers | No | 2025-12-31 |  | 2025-04-09 | Completed |  | DD-MMM-YY | TCN has been unbundled into NISO and TSP(TCN) |  | Congratulations
NGA | 1 | 1 | #NAME? | 09 | Integrated least-cost power system planning adopted incorporating regional resources | NERC completes the MYTO Extraordinary Review and issues a new MYTO for the period 2024-2026 for TCN, redefining allowances on CAPEX, OPEX, and losses consistent with the PIP | No | 2028-12-31 |  | 2025-05-14 | Completed |  | DD-MMM-YY | NERC issued an order on PIP for TCN and NISO on 14/05/25. The MYTO Review for TCN will feedoff from the PIP |  | Congratulations
NGA | 1 | 1 | #NAME? | 10 | Integrated least-cost power system planning adopted incorporating regional resources | Review the NDCs and the ETP to ensure alignment with evolving global climate commitments and the country’s sustainable energy goals | No | 2025-12-31 |  | 2025-09-01 | Completed |  | DD-MMM-YY | The NCCC has finalised the NDC 3.0 |  | Congratulations
NGA | 1 | 1 | #NAME? | 11 | Integrated least-cost power system planning adopted incorporating regional resources | Prepare a Gas Master Plan and gas flaring policy consistent with Nigeria’s 2060 net zero targets as provided by the energy transition plan and the NDCs | No | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | The Gas Master Plan was last reviewed in 2006; hence, M300 will support the Ministry for Gas and Petroleum in reviewing and updating the Plan with the current best practices. However, the Gas Flaring Policy is complete and institutionalised. |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 12 | Integrated least-cost power system planning adopted incorporating regional resources | Ministry of Power prepares the Hydro Power Master Plan | No | 2027-12-31 |  |  | On Track |  | DD-MMM-YY | An EOI has been issued, and submissions are expected to be concluded by the 20th of January. Afterwards, the RFP is expected in February 2026. Currently being developed by the Ministry of Power and the Ministry of Water Resources (World Bank, SPIN Programme). This is expected to be completed within 18 months. |  | Well noted - thanks for the comment
NGA | 1 | 1 | #NAME? | 13 | Integrated least-cost power system planning adopted incorporating regional resources | Under the leadership of the Ministry of Power, Bureau of Public Enterprises (BPE) and the Infrastructure Concession Regulatory Commission (ICRC) to develop a PPP framework for investment in large hydropower projects | No | 2028-12-31 |  |  | On Track |  | DD-MMM-YY | There is an existing PPP Framework, which is currently being reviewed to reflect the current realities in the sector, hence there is no need to develop a new PPP framework. |  | Well noted - thanks for the comment
[5 empty] | Integrated least-cost power system planning adopted incorporating regional resources | Deployment of SCADA systems for real-time monitoring and load management. | Yes | 2026-12-31 |  |  | Delayed |  | DD-MMM-YY |  |  | SEForALL: Identified as a top 10 priority actions but not included in the tracker nor the original compact. We considered as "new action" identified by the CDMU can you kindly confirm? If so, please inform about status and expected completion date in comment. Thank you!
[5 empty] | Integrated least-cost power system planning adopted incorporating regional resources | Development of an updated National Integrated Resource Plan incorporating the new transmission expansion plan | Yes | 2026-12-31 |  |  | Delayed |  | DD-MMM-YY |  |  | SEForALL: Identified as a top 10 priority actions but not included in the tracker nor the original compact. We considered as "new action" identified by the CDMU can you kindly confirm? If so, please inform about status and expected completion date in comment. Thank you!
NGA | 1 | 2 | #NAME? | 01 | Competitive procurement policy and framework in place for private-sector investment in renewable energy | Framework set out for competitive procurement procedures | No | 2025-06-30 |  |  | Completed |  | DD-MMM-YY | The Framework for competitive procurement has been developed by the WB (Solar Auction Framework) |  | Congratulations, Please kindly insert date in "actual completion column" as this action is completed
NGA | 1 | 2 | #NAME? | 02 | Competitive procurement policy and framework in place for private-sector investment in renewable energy | The Regulator approves a framework and roadmap for transitioning to bilateral contracts | No | 2027-12-31 |  |  | Delayed |  | DD-MMM-YY | The order has been issued by the Regulator, but the FG has put a hold on transitioning to bilateral contracts due to some pending market illiquidity issues.
NGA | 1 | 2 | #NAME? | 03 | Competitive procurement policy and framework in place for private-sector investment in renewable energy | Regulator approves provisions on how existing and new energy must be competitively procured by off-takers | No | 2027-12-31 |  |  | Delayed |  | DD-MMM-YY | The market liquidity have to improve before new generation capacity is brought onto the grid. The short term focus is to bring stranded existing capacity on the grid
NGA | 1 | 2 | #NAME? | 04 | Competitive procurement policy and framework in place for private-sector investment in renewable energy | Regulator implements first auction to procure new generation capacity in consistency with 2024 bilateral contracts roadmap | No | 2027-12-31 |  |  | Delayed |  | DD-MMM-YY | The market liquidity have to improve before new generation capacity is brought onto the grid. The short term focus is to bring stranded existing capacity on the grid
NGA | 1 | 2 | #NAME? | 05 | Competitive procurement policy and framework in place for private-sector investment in renewable energy | Building on the NIEP, the SIP with detailed actionable strategies to strengthen capacity development across the electricity sector | Yes | 2026-07-31 |  |  | In Progress-On Track |  | DD-MMM-YY | The SIP is currently being developed and projected to be completed by end of Q2 2026
NGA | 1 | 2 | #NAME? | 06 | Competitive procurement policy and framework in place for private-sector investment in renewable energy | Enable investment into development of domestic supply chains by incorporating standards and local content opportunities within national and sub-national programmes | No | 2026-06-30 |  |  | Delayed |  | DD-MMM-YY | This is currently in the NIEP and will be implemented as soon as the SIP is completed and institutionalised
Pillar II Work towards financially viable utilities that provide reliable service
NGA | 2 | 1 | #NAME? | 01 | Adopt and enforce harmonized transmission pricing within the respective power pools to facilitate the power trade across borders | Adoption of a Transmission Charging Model | No | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | M300 to develop a framework for the private sector participation on the Transmission Grid (Case studies from Kenya, Brazil and India to be reviewed)
NGA | 2 | 1 | #NAME? | 02 | Adopt and enforce harmonized transmission pricing within the respective power pools to facilitate the power trade across borders | ECOWAS Master Plan for Power Generation and Transmission | No | 2033-12-31 |  |  | On Track |  | DD-MMM-YY | M300 to conduct studies to unlock stranded power to drive interconnected transmission projects
NGA | 2 | 1 | #NAME? | 03 | Adopt and enforce harmonized transmission pricing within the respective power pools to facilitate the power trade across borders | Synchronization of West African Grids | Yes | 2026-03-31 |  |  | In Progress-On Track |  | DD-MMM-YY | A 4-hour successful synchronization test was achieved on November 8th 2025
Pillar III Incentivize private sector participation to unlock additional resources
NGA | 3 | 1 | #NAME? | 01 | Monitoring and evaluation program adopted to track the MTF (Multi-Tier Framework) for access to electricity and clean cooking | A follow on survey and analysis to expand the MTF to all of Nigeria to be completed | No | 2026-06-30 |  |  | On Track |  | DD-MMM-YY | The NESIP phase 1 has been developed and finalised as a working document, and the REA awaits approval from the NEC. The REA has initiated preliminary activities for NESIP 2, which will follow a specific sector-targeted plan. Regarding the MTF, the WB, through the REA, has signed the MOU with NBS and engaged NBS, REA, WB ESMAP, and the consultant in implementing the survey. The survey is expected to begin in March 2026. The sampling framework and survey questions are currently under review.
NGA | 3 | 1 | #NAME? | 02 | Monitoring and evaluation program adopted to track the MTF for access to electricity and clean cooking | Regular updates to the MTF to be carried out at a regular cadence to measure progress towards electrification and clean cooking targets | No | 2026-06-30 |  |  | Delayed |  | DD-MMM-YY | There should be separate indicators for Clean Cooking, as it is now a separate pillar. This will be discussed during the upcoming working group engagement.
NGA | 3 | 1 | #NAME? | 03 | Monitoring and evaluation program adopted to track the MTF for access to electricity and clean cooking | A data platform for M&E to be established | No | 2025-03-31 |  |  | Delayed |  | DD-MMM-YY | There should be a separate indicator for clean cooking. The data platform has been developed for access to electricity, but is yet to be operationalised.
NGA | 3 | 2 | #NAME? | 01 | National Electrification Strategy and Implementation Plan(NESIP) adopted including an updated five-year electrification plan with a clearly defined role for private sector | Update and approve the NESIP | Yes | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | The NESIP phase 1 has been developed and finalised as a working document, and the REA awaits approval from the NEC. |  | Please note that the Status should be delayed (not in progress minor delays) as expected deadline passed - we modified in this excel verion and considered as delayed in the CPR Report.
NGA | 3 | 2 | #NAME? | 02 | National Electrification Strategy and Implementation Plan(NESIP) adopted including an updated five-year electrification plan with a clearly defined role for private sector | Approval of the National Action Plan on Gender Mainstreaming in Energy Access | Yes | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | The National Action Plan on Gender Mainstreaming in Energy Access is currently being developed and will be concluded and finalised in March 2026 |  | Please note that the Status should be delayed (not in progress minor delays) as expected deadline passed - we modified in this excel verion and considered as delayed in the CPR Report.
NGA | 3 | 2 | #NAME? | 03 | Scale proven governance frameworks for DRE procurement and implementation | Replicable Framework for DRE Implementation | No | 2025-12-31 |  |  | On Track |  | DD-MMM-YY | The NESIP is the Framework for the DRE Implementation, which has been developed and awaiting approval for operationalisation
NGA | 3 | 3 | #NAME? | 01 | National clean cooking strategy in place | FEC Approval of a Clean Cooking Policy | No | 2024-12-31 |  | 2024-03-25 | Completed |  | DD-MMM-YY | This was submitted by the Ministry of Environment and approved by FEC in March 2024 - This should be an indicator for the clean cooking Pillar |  | Congratulations!
NGA | 3 | 4 | #NAME? | 01 | Policy and regulatory framework adopted for offgrid and clean cooking solutions | Adopt revised and harmonized policies and regulations for mini-grids, off-grid solar and clean cooking | No | 2025-12-31 |  | 2024-12-29 | Completed |  | DD-MMM-YY | The Clean Cooking Policy has been approved and is currently being operationalised. Regulations for minigrids and off-grids have also been operationalized. |  | Congratulations!
Pillar IV Embrace distributed renewable energy (DRE) and clean cooking solutions for affordable last-mile access
NGA | 4 | 1 | #NAME? | 01 | Process outlined for regulatory approval of private-sector-led mini-grids (including tariff regulations) | Licensing limits (increase from 1 MW and above for mini grids with technical requirements compliant with grid code for seamless interconnection with the grid in future) | Yes | 2026-06-30 |  |  | In Progress-On Track |  | DD-MMM-YY | The current licensing limit for minigrid and off-grid is less than 1MW, but the mini-grid regulation currently being reviewed. However, a derogation has been granted by NERC to increase the limit and accomodate 42 interconnected mini-grid sites under DARES program with capacity ranging between 0.9MW and 10MW (average capacity of 5.879MW). The guidelines for the commercial framework for the minigrids was released in December 2025
NGA | 4 | 1 | #NAME? | 02 | Process outlined for regulatory approval of private-sector-led mini-grids (including tariff regulations) | Quicker, streamlined processing of registration, licensing and tariff applications | No | 2026-06-30 |  |  | On Track |  | DD-MMM-YY | This will be addressed as soon as the minigrid regulation is approved
NGA | 4 | 1 | #NAME? | 03 | Process outlined for regulatory approval of private-sector-led mini-grids (including tariff regulations) | Introducing a net billing policy to incentivize consumers to become producers | Yes | 2026-06-30 |  |  | In Progress-On Track |  | DD-MMM-YY | The draft net metering regulation is completed and yet to be operationalised
NGA | 4 | 1 | #NAME? | 04 | Process outlined for regulatory approval of private-sector-led mini-grids (including tariff regulations) | Better contract management and dispute resolution | No | No date listed |  |  |  |  | DD-MMM-YY | This indicator may not be necessary and should be removed. |  | noted but listed in initial compact - If you confirm we can remove this line in the next data collection cycle
NGA | 4 | 1 | #NAME? | 05 | Process outlined for regulatory approval of private-sector-led mini-grids (including tariff regulations) | Updated tariff regulations including, where possible, harmonization at state levels, including adjustments based on macro costs | No | No date listed |  |  |  |  | DD-MMM-YY | This indicator is currently not applicable |  | noted but listed in initial compact - If you confirm we can remove this line in the next data collection cycle
NGA | 4 | 2 | #NAME? | 01 | Financial support to private sector DRE and clean cooking operators ensures affordability and aviability | Existing legal and commercial framework to unlock, expedite, and scale access to long-term local currency capital for distributed renewable energy (DRE) projects | No | 2025-12-31 |  |  | On Track |  | DD-MMM-YY | The NESIP is the Framework for the DRE Implementation, which is currently being developed
NGA | 4 | 2 | #NAME? | 02 | Financial support to private sector DRE and clean cooking operators ensures affordability and aviability | Establish/scale-up results-based financing (RBF) facility for distributed renewable energy | No | 1905-07-17 |  | 2025-08-22 | Completed |  | DD-MMM-YY |  |  | Congratulations!
|  |  | #NAME? |  | Pillar V Leverage the benefits of increased regional integration
NGA | 5 | 2 | #NAME? | 01 | Utilities achieving at least 100 percent operational cost recovery | Periodic (quarterly) adjustments and enforcement of tariffs adjustments based on macroeconomic factors with a path towards cost reflectivity | No | 2025-03-31 |  |  | On Track |  | DD-MMM-YY | The supplementary tariff review was conducted by NERC in May 2025, and outstanding liabilities to be validated and liquidated
NGA | 5 | 2 | #NAME? | 02 | Utilities achieving at least 100 percent operational cost recovery | Put in place a subsidy scheme that provides a universal and flat limited subsidy to each connected customer | Yes | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | The process to implement a targeted subsidy scheme for the economically vulnerable is underway |  | Please note that the Status should be delayed (not in progress minor delays) as expected deadline passed - we modified in this excel verion and considered as delayed in the CPR Report.
NGA | 5 | 2 | #NAME? | 03 | Utilities achieving at least 100 percent operational cost recovery | Develop, on an ongoing basis, a funding plan to finance subsidies due to non-cost reflective tariffs | No | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | FGN is looking to review the end-user tariff to ensure cost reflectivity and operationalise the PCAF to support the vulnerable customers with less than 100kWh/month. Both the tariff review and the operatioanlisation of PCAF will be implemented under the existing subsidy management (i.e., MRO)
NGA | 5 | 2 | #NAME? | 04 | Utilities achieving at least 100 percent operational cost recovery | Approval of the Power Sector Debt resolution scheme for GENCOs and Discos on arrears owed by FG as a line item in the 2025 budget. | Yes | 2024-12-31 |  |  | Delayed |  | DD-MMM-YY | The Presidential Power Sector Debt Reduction Programme is ongoing. The settlement plans combine two methods: budgetary allocations and government-backed bonds. In December 2025, the first Series of these bonds, worth 590 billion Naira, was issued under a 4 trillion Naira Multi-Instrument Issuance Programme. The Bond issuance programme is expected to continue in 2026. |  | Please note that the Status should be delayed (not in progress minor delays) as expected deadline passed - we modified in this excel verion and considered as delayed in the CPR Report.
NGA | 5 | 2 | #NAME? | 05 | Utilities achieving at least 100 percent operational cost recovery | NERC approves updated Metering Code | No | 2027-12-31 |  |  | On Track |  | DD-MMM-YY | NERC is in the process of updating the metering codes
NGA | 5 | 2 | #NAME? | 06 | Utilities achieving at least 100 percent operational cost recovery | FGN through SGDL approves in 2024 a Metering Plan to close the metering gap in the period 2025 to 2027 | No | 2027-12-31 |  |  | On Track |  | DD-MMM-YY | Under ICB1 (1.437 million smart meters): 408,471 meters delivered, but only 77,244 installed as at 5 December 2025. Average installation progress across Lots 1–4 stands at 43.79%, while Lot 5 lags at 21.21%. Several DisCos have received substantial meter volumes.
NGA | 5 | 2 | #NAME? | 07 | Utilities achieving at least 100 percent operational cost recovery | Deployment of key Management Information Systems (MIS) - including commercial and outage management systems – by all DisCos | No | 2027-12-31 |  |  | On Track |  | DD-MMM-YY | Contract negotiations were suspended pending clarification of pricing structures and cost drivers. MIS deployment is incomplete and fragmented, and the Committee is pushing for harmonisation, transparency in pricing, and future-proof systems capable of integrating meters from multiple initiatives.
NGA | 5 | 2 | #NAME? | 08 | Utilities achieving at least 100 percent operational cost recovery | Ensuring implementation of DISCO’s (PIPs) and hold them responsible for them | No | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | All DisCos have Signed the Shareholders' Loan Agreement (SHLA). Submitted Board Resolutions. Submitted Individual Action Plans (IAPs), except JEDC
NGA | 5 | 2 | #NAME? | 09 | Utilities achieving at least 100 percent operational cost recovery | Provide seed financing for PIP to enable DISCOs to access commercial financing later | No | 2025-12-31 |  |  | Delayed |  | DD-MMM-YY | All DisCos have Signed the Shareholders' Loan Agreement (SHLA). Submitted Board Resolutions. Submitted Individual Action Plans (IAPs), except JEDC
NGA | 5 | 2 | #NAME? | 10 | Utilities achieving at least 100 percent operational cost recovery | Focus on commercial losses and low collections first and set aggressive targets | No | No specific date |  |  |  |  | DD-MMM-YY | This indicator may not be necessary and should be removed. |  | noted but listed in initial compact - If you confirm we can remove this line in the next data collection cycle
NGA | 5 | 2 | #NAME? | 11 | Utilities achieving at least 100 percent operational cost recovery | NERC approves TCN’s PIP for next 5 years with redefining allowances on CAPEX, OPEX and losses, consistent with the PIP and ensure funding is available with yearly targets of improvements | No | 2025-12-31 |  | 2025-05-14 | Completed |  | DD-MMM-YY |  |  | Congratulations!
NGA | 5 | 2 | #NAME? | 12 | Utilities achieving at least 100 percent operational cost recovery | Prepare and approve a strategy and road map to address the situation of distressed privatized DISCOs | No | 2025-12-31 |  |  | On Track |  | DD-MMM-YY | FGN is reviewing poor performing DISCOs and will implement a framework to improve performance
NGA | 5 | 2 | #NAME? | 13 | Utilities achieving at least 100 percent operational cost recovery | Strengthen regulatory oversight of the distribution companies | No | 2025-12-31 |  |  | On Track |  | DD-MMM-YY | BPE has taken a stronger position on the board of the DISCOs to ensure better performance. NERC continues to drive strong regulatory oversight in States that do not have regulatory autonomy.

## Nigeria Targets (Old) (hidden)
Country Code | Target Code | Indicator Code | Technology Code | Target | Technology | Baseline | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | End value | Comments
|  |  |  | Electricity access (select units) | No. of People
NGA | EA | 1 | 02 | Target: Electricity access | Grid |  | 130000000 | 145000000 | 160000000 | 175000000 | 190000000 | 200000000 |  | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 2 | 02 | Actual # of people provided with electricity | Grid |  | 114000000 | [6 empty] | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 3 | 02 | Actual cumulative progress | Grid |  | 87.69% | 0% | 0% | 0% | 0% | 0%
NGA | EA | 4 | 02 | % of cumulative progress against the end target | Grid |  | 57% | 0% | 0% | 0% | 0% | 0%
NGA | EA | 1 | 03 | Target: Electricity access | Off-grid |  | 9800000 | 11000000 | 12300000 | 14000000 | 17000000 | 20000000 |  | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 2 | 03 | Actual # of people provided with electricity | Off-grid |  | 8200000 | [6 empty] | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 3 | 03 | Actual cumulative progress | Off-grid |  | 83.67% | 0% | 0% | 0% | 0% | 0%
NGA | EA | 4 | 03 | % of cumulative progress against the end target | Off-grid |  | 41% | 0% | 0% | 0% | 0% | 0%
NGA | EA | 1 | 04 | Target: Electricity access | Mini-grid |  | 2000000 | 3200000 | 4400000 | 5400000 | 6400000 | 6800000 |  | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 2 | 04 | Actual # of people provided with electricity | Mini-grid |  | 850000 | [6 empty] | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 3 | 04 | Actual cumulative progress | Mini-grid |  | 42.5% | 0% | 0% | 0% | 0% | 0% |  | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 4 | 04 | % of cumulative progress against the end target | Mini-grid |  | 12.5% | 0% | 0% | 0% | 0% | 0% |  | Actuals beyond 2023 are not yet available. Progress % from 2024–2029 assumes static 2023 values until updated. Source: NIRP 2024.
NGA | EA | 1 | 05 | Target: Electricity access | SHS |  | 7800000 | 8400000 | 8900000 | 9400000 | 9800000 | 9900000 |  | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 2 | 05 | Actual # of people provided with electricity | SHS |  | 7271070 | [6 empty] | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 3 | 05 | Actual cumulative progress | SHS |  | 93.22% | 0% | 0% | 0% | 0% | 0% |  | Source: NIRP 2024, NESIP Least Cost Model, REA Reports.
NGA | EA | 4 | 05 | % of cumulative progress against the end target | SHS |  | 73.45% | 0% | 0% | 0% | 0% | 0%
NGA | EA | 5 | 01 | WBG supported # of people | All |  |  | 2628652 | 5257304 | 9638391 | 140190478 | 16224500 |  | Source: DARES program result framework
NGA | EA | 6 | 01 | AfDB supported # of people | All | [8 empty] | Pending
|  |  |  | Total Targets |  |  | 149600000 | 167600000 | 185600000 | 203800000 | 223200000 | 236700000
|  |  |  | Total Actuals |  |  | 130321070
Clean cooking (% of population)
NGA | CC | 1 | 99 | Target: Clean cooking |  | 26% | 41% | 52% | 68% | 86.5% | 100% | 100% |  | Source: UNDP Clean Cooking Model, NIRP 2024, NESIP Least Cost Model.
NGA | CC | 2 | 99 | Actual % of people provided with clean cooking |  | 26% | 40.8% | [6 empty] | Source: UNDP Clean Cooking Model, NIRP 2024, NESIP Least Cost Model.
Renewable Energy Share (% of generation)
NGA | RE | 1 | 99 | Target: Increase share of renewable energy |  | 22% | 29% | 29.83% | 30.67% | 31.5% | 33% | 34% |  | NESIP Least Cost Model, REA Reports
NGA | RE | 2 | 99 | Actual share of renewable energy |  | 22% | 22%
Funding needs (US$ Million)
NGA | FA | 1 | 23 | Target: Funding needs from public sector | Generation |  | 500 | 500 | 500 | 500 | 500 | 500 | 3000 | Pending
NGA | FA | 2 | 23 | Actual public funding | Generation | [7 empty] | 0 | Pending
NGA | FA | 3 | 23 | Actual cumulative progress | Generation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FA | 4 | 23 | % of cumulative progress against the end target | Generation |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Pending
NGA | FB | 1 | 23 | Target: Funding needs from private sector | Generation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FB | 2 | 23 | Actual private funding | Generation | [7 empty] | 0 | Pending
NGA | FB | 3 | 23 | Actual cumulative progress | Generation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FB | 4 | 23 | % of cumulative progress against the end target | Generation | [8 empty] | Pending
NGA | FA | 1 | 20 | Target: Funding needs from public sector | Transmission |  | 883.3 | 883.3 | 883.3 | 883.3 | 883.3 | 883.3 | 5299.8 | Pending
NGA | FA | 2 | 20 | Actual public funding | Transmission | [7 empty] | 0 | Pending
NGA | FA | 3 | 20 | Actual cumulative progress | Transmission |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FA | 4 | 20 | % of cumulative progress against the end target | Transmission |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Pending
NGA | FB | 1 | 20 | Target: Funding needs from private sector | Transmission |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FB | 2 | 20 | Actual private funding | Transmission | [7 empty] | 0 | Pending
NGA | FB | 3 | 20 | Actual cumulative progress | Transmission |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FB | 4 | 20 | % of cumulative progress against the end target | Transmission | [8 empty] | Pending
NGA | FA | 1 | 21 | Target: Funding needs from public sector | Distribution |  | 566.7 | 566.7 | 566.7 | 566.7 | 566.7 | 566.7 | 3400.2 | Pending
NGA | FA | 2 | 21 | Actual public funding | Distribution | [7 empty] | 0 | Pending
NGA | FA | 3 | 21 | Actual cumulative progress | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FA | 4 | 21 | % of cumulative progress against the end target | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Pending
NGA | FB | 1 | 21 | Target: Funding needs from private sector | Distribution |  | 850 | 850 | 850 | 850 | 850 | 850 | 5100 | Pending
NGA | FB | 2 | 21 | Actual private funding | Distribution | [7 empty] | 0 | Pending
NGA | FB | 3 | 21 | Actual cumulative progress | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FB | 4 | 21 | % of cumulative progress against the end target | Distribution |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Pending
NGA | FA | 1 | 03 | Target: Funding needs from public sector | Off-grid |  | 71.7 | 71.7 | 71.7 | 71.7 | 71.7 | 71.7 | 430.2 | Pending
NGA | FA | 2 | 03 | Actual public funding | Off-grid | [7 empty] | 0 | Pending
NGA | FA | 3 | 03 | Actual cumulative progress | Off-grid |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FA | 4 | 03 | % of cumulative progress against the end target | Off-grid |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Pending
NGA | FB | 1 | 03 | Target: Funding needs from private sector | Off-grid |  | 1750 | 1750 | 1750 | 1750 | 1750 | 1750 | 10500
NGA | FB | 2 | 03 | Actual private funding | Off-grid | [7 empty] | 0 | Pending
NGA | FB | 3 | 03 | Actual cumulative progress | Off-grid |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Pending
NGA | FB | 4 | 03 | % of cumulative progress against the end target | Off-grid |  | 0 | 0 | 0 | 0 | 0 | 0 |  | Pending
NGA | FA | 1 | 18 | Target: Funding needs from public sector | Clean Cooking |  | 226.35 | 243.59 | 260.83 | 278.07 | 295.31 | 312.55 | 1616.7 | Source: UNDP Clean Cooking Model, NIRP 2024, NESIP Least Cost Model.
NGA | FA | 2 | 18 | Actual public funding | Clean Cooking | [8 empty] | Annual data not available. Value reflects aggregate or modelled estimates. Sources: NIRP 2024, NESIP Least Cost Model, PowerForAll/GOGLA 2025,
NGA | FA | 3 | 18 | Actual cumulative progress | Clean Cooking | [8 empty] | Annual data not available. Value reflects aggregate or modelled estimates. Sources: NIRP 2024, NESIP Least Cost Model, PowerForAll/GOGLA 2025,
NGA | FA | 4 | 18 | % of cumulative progress against the end target | Clean Cooking | [8 empty] | Annual data not available. Value reflects aggregate or modelled estimates. Sources: NIRP 2024, NESIP Least Cost Model, PowerForAll/GOGLA 2025,
NGA | FB | 1 | 18 | Target: Funding needs from private sector | Clean Cooking |  | 170.76 | 183.76 | 196.76 | 209.76 | 222.76 | 235.76 | 1219.56 | Source: UNDP Clean Cooking Model, NIRP 2024, NESIP Least Cost Model.
NGA | FB | 2 | 18 | Actual private funding | Clean Cooking | [8 empty] | Annual data not available. Value reflects aggregate or modelled estimates. Sources: NIRP 2024, NESIP Least Cost Model, PowerForAll/GOGLA 2025,
NGA | FB | 3 | 18 | Actual cumulative progress | Clean Cooking | [8 empty] | Annual data not available. Value reflects aggregate or modelled estimates. Sources: NIRP 2024, NESIP Least Cost Model, PowerForAll/GOGLA 2025,
NGA | FB | 4 | 18 | % of cumulative progress against the end target | Clean Cooking | [8 empty] | Annual data not available. Value reflects aggregate or modelled estimates. Sources: NIRP 2024, NESIP Least Cost Model, PowerForAll/GOGLA 2025,
Private capital mobilized (US$ million)
NGA | PC | 1 | 99 | Target: Increase amount of private capital mobilized |  |  | 2583.3 | 2583.3 | 2583.3 | 2583.3 | 2583.3 | 2583.3 | 15499.8
NGA | PC | 2 | 99 | Actual private capital mobilized | [8 empty] | 0
NGA | PC | 3 | 99 | Actual cumulative progress |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
NGA | PC | 4 | 99 | % of cumulative progress against the end target |  |  | 0 | 0 | 0 | 0 | 0 | 0

## Nigeria Targets
Target | Baseline* | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | End value | Data Entry Guidelines | New Comments from CDMU
Electricity access (No. of people)
Target: Electricity access |  | 149600000 | 167600000 | 185600000 | 203800000 | 223200000 | 236700000 |  | Note: Please provide year on year targets for electricity access represented as "Number of People" with new access to electricity
Target new # of people provided with electricity |  |  | 18000000 | 18000000 | 18200000 | 19400000 | 13500000 | 87100000
Actual # of people provided with electricity | 86600000 | 137300000 | [6 empty] | Note: Please provide baseline figure (ideally 2024) for electricity access represented as "Number of People" with access + 2025 & 2026 figure with new number of people with electricity
Actual # of households provided with electricity | [8 empty] | Note: Please provide the 2025, 2026 figure of new number of households connection (if number of people with electricity is not available)
Household coefficient (average number of people per household) | [8 empty] | Note: If the data available is Actual Number of households provided with electriicty, then please provide the household coefficient for the appropriate year.
Clean cooking (% of population)
Target: Clean cooking |  | 41% | 52% | 68% | 86.5% | 100% | 100% | 100% | Note: Please provide indicative targets per year as "% of population"
Actual % of people provided with clean cooking | 22% | 26% | [6 empty] | Note: Please verify baseline as "% of population" with year of reference in comment column + include actual figure for 2025 if available
Renewable Energy Share (% of generation)
Target: Increase share of renewable energy |  | 29% | 29.83% | 30.67% | 31.5% | 33% | 34% | 75% | Note: Please provide targets per year as "% of generation"
Actual share of renewable energy | 22% | 38.8% | [6 empty] | Note: Please verify baseline as "% of generation" with year of reference in comment column + include actual figure for 2025 if available
Private capital mobilized (US$ million)
Target: Increase amount of private capital mobilized |  | 2583.3 | 2583.3 | 2583.3 | 2583.3 | 2583.3 | 2583.3 | 15499.8 | Note: Figures caluclated based on compact target and baseline. Please verify/modify
Actual private capital mobilized | [8 empty] | Note: Please verify baseline with year of referencewith year of reference in comment column + include actual figure for 2025 if available
* Baselines are needed to support analyses. Please include baselines - the baseline value would be number of people with access in the year before M300 activities began

## Data Validation (hidden)
NoList | YesList | Colour Code
On Track | Not Yet Due | No colour
Delayed | In Progress-On Track
Completed | In Progress-Minor Delays
| In Progress-At Risk | Orange
| Delayed | Red
Completed