## About
M300 Monitoring Platform | Backend review
Prepared | 25 August 2026
Backend reviewed | https://nigeria.geappindia.org/api
Method | Exercised the live API as a signed-in client (one administrator session) and compared responses against our published API contract (docs/API.md and the shared HTML version, sent previously). Every finding below is either an HTTP response we observed, or a place where the response does not match what that document specifies. No write actions were performed except where noted.
Scope | The whole dashboard, not only document upload.
Data provided so far | The one dataset shared with the backend team to date is the compiled NERC workbook (metering, ATC&C, generation capacity and remittance records). Figures for KPIs outside that dataset — electricity access rate, clean cooking access, private capital mobilised — do not yet have a source we have sent. Items in Gap Register note this where it applies. As further datasets are ready we will share them.
How to read this | Gap Register lists behaviour that does not match our published contract, with what we observed and the requested action. Contract Updates Needed lists capability the frontend has gained since the contract was last shared, which was never specified to the backend and is therefore on us to formalise before asking for it to be built. Endpoint Inventory is the observed state of every route we call. Questions for Backend Team is what we would like a written response on.
Severity | Critical: the module shows results that do not appear to be live, or a security control is unconfirmed. High: a documented capability is missing or a module cannot load. Medium: behaviour does not match the contract but has a workaround. Low: minor or easily corrected.
A note on some items | A few rows record something we could not verify (e.g. SE-02, DS-03) rather than something we found wrong, and are included so the list reflects what is confirmed versus what still needs a test on both sides.
Counts | Gap Register: 34 items · 6 critical · 6 high · 14 medium · 8 low. Contract Updates Needed: 8 items.

## Gap Register
ID | Module | Severity | Item | What we observed | Impact | Requested action | Owner | Target date | Status
DS-01 | Data Submission | Critical | Uploaded data is not reflected in the review outcome | A submission in the review queue was created from a real, fully-populated NERC data file. Its extracted Metering Rate value is 57.4%, identical to the figure already shown elsewhere on the platform before this file was ever uploaded. | A custodian cannot tell whether their return was actually processed, since the same value appears regardless of what was submitted. | Confirm the extracted value is calculated from the uploaded file's contents, per API.md §Data Submissions ("parsing the uploaded file... running the dataset's calculation formula... is backend responsibility").
DS-02 | Data Submission | High | Validation result does not vary | The one submission we could inspect in the review queue shows automatedCheck: pass, issueCount: 0, and "Automated checks passed with 0 issues" as its summary. | If this does not vary by content, an incorrect or incomplete return would be told it passed. | Confirm field-level and business-rule validation is applied per submission, per API.md's issues[] contract.
DS-03 | Data Submission | Critical | Approval outcome could not be confirmed to reach the KPI record | Not tested directly (no write actions were issued during this review). Flagged because API.md states approval "is the point where a KPI's current value and history actually change" and must update KpiProfile.current, append a history point with the submission id, and set the obligation's acceptedSubmissionId. | If this path is incomplete, an approved submission would not actually update the KPI it was meant to publish. | Confirm end-to-end: approve a test submission and verify the KPI's current value, history and the obligation's acceptedSubmissionId all update.
DS-04 | Data Submission | Medium | Downloaded template is not a spreadsheet file | Downloading the current template for Metering Rate returns a 50-byte file with a spreadsheet Content-Type and .xlsx filename. The file's content is a single line of comma-separated column names, not spreadsheet-format data. | Recipients whose spreadsheet software validates file format may reject or warn on the download. | Confirm templates are generated in genuine spreadsheet format, per API.md's template-download contract.
DS-05 | Data Submission | Medium | Template columns do not identify which utility or period a row describes | The downloaded template's three columns are metered_customers, total_customers, reporting_notes — no DisCo, state or reporting-period column. | A completed return cannot be attributed to a specific utility or quarter. | Include identifying columns (DisCo, state, reporting period) derived from the dataset's field definitions.
DS-06 | Data Submission | High | Obligation due-status labels do not match their due dates | On the date this was checked, one obligation with a due date roughly seven weeks in the future was labelled "overdue" and appeared in the overdue list; another due in about seven weeks was labelled "due in 5 days". | Compliance tracking based on this list would flag obligations as breached before their deadline, or miss ones that are genuinely close. | Confirm due/overdue status is computed from dueDate against the current date.
DS-07 | Data Submission | Low | Reviewer is shown before any review has occurred | The one submission we could inspect shows a named reviewer while its status is still "pending review", i.e. before any decision has been recorded. | The reviewer field may not reflect who actually reviews the submission. | Confirm reviewer is set at the point of decision, not before.
DS-08 | Data Submission | Medium | Extracted value references a KPI identifier not used elsewhere on the platform | The submission detail response identifies its extracted value with kpiId "M300-P3-004". Every KPI id returned by GET /kpi-explorer is a small integer (e.g. 8). | Even if DS-03 is resolved, this value could not be matched to a KPI record using the platform's own identifiers. | Use one consistent KPI identifier scheme across Data Submissions and KPI Explorer.
EO-01 | Executive Overview | Critical | Headline figures do not change between requests | The lastUpdated field on this response has not changed across repeated calls over several hours, and the four headline figures (people with access, access rate, generation capacity, clean cooking access) are identical every time regardless of the filters applied (see EO-02). | The dashboard's primary figures cannot be confirmed to reflect current monitored data. | Confirm this endpoint is served from live records, per API.md's Executive Overview contract.
EO-02 | Executive Overview | Critical | Headline figures do not change when a Compact pillar is selected | Calling this endpoint with pillar=clean-cooking returns the same four headline values as the unfiltered call, while the national-performance and ongoing-projects lists both become empty. The response's own appliedPillar field confirms the filter was received. | A reader sees the national totals labelled under a single pillar's heading, which reads as that pillar's own figures. | Apply the filter to every section of the response, per API.md: "the backend must apply every supplied parameter before returning the payload."
EO-03 | Executive Overview | High | Headline figures do not change when a reporting period is selected | Calling this endpoint with period=q1-2025 (a real value from GET /filters) returns a response identical, field for field, to the default call. | A prior reporting period cannot be viewed on this page. | Apply the period filter to the response, per API.md's filter contract.
EO-04 | Executive Overview | Medium | Access-delivery and exception sections do not change with the pillar filter | Both sections return the same row count under pillar=clean-cooking as under the unfiltered call. | Inconsistent with the sections that do respond to the same filter. | Apply the filter consistently across all sections.
CT-01 | Contract | High | cprTargets is not present in the response | API.md specifies this as a required array of four entries. It is absent from the live response. | The CPR-target framing documented for this page cannot be shown. | Add per API.md.
CT-02 | Contract | Medium | kpiId is not present on any of the four headline cards | Required per API.md so each card can link to its KPI Explorer profile. | The deep-link from Executive Overview into KPI Explorer cannot be built. | Add per API.md, or null where a figure is genuinely composite.
CT-03 | Contract | Medium | milestones is not present on two of the four headline cards | Required per API.md for the two Compact-outcome cards. | Interim checkpoints cannot be shown against the approved trajectory. | Add per API.md, or an empty array where none are defined yet.
CT-04 | Contract | Medium | history is not present on the national-performance metrics | Required per API.md, ordered oldest-to-newest with a period label per point. | No trend view can be shown for these metrics. | Add per API.md.
CT-05 | Contract | Medium | Sparkline values are not period-labelled | API.md specifies each point as {period, value}. The response sends plain numbers. | A real time axis cannot be drawn for these series. | Send {period, value} pairs per API.md.
CT-06 | Contract | Low | Four fields on ongoing projects are not present | leadName, comment, pipelineReadiness and statusHistory are all specified in API.md and absent from the response. | The project lead, latest comment, pipeline-readiness badge and status-history table cannot be shown. | Add per API.md, using null/empty where genuinely not yet available.
CT-07 | Contract | Low | followUp is not present on exception rows | Specified in API.md for the bottleneck register. | The register cannot show what is being done about an unresolved exception. | Add per API.md.
PD-01 | Pillar Dashboard | Critical | Every pillar page returns "not found" | GET /api/pillars/generation-network (and every other pillar slug the frontend requests) returns 404 "Unknown pillar". The same endpoint accepts small integers instead. API.md specifies the six named pillar values explicitly for this route. | The entire Pillar Dashboard module cannot load for any pillar. | Accept the pillar identifiers specified in API.md at this endpoint.
KE-01 | KPI Explorer | High | Pillar is returned as a number instead of the documented value | GET /kpi-explorer returns each row's pillar as a small integer. API.md and the published schema specify one of the six named pillar values. | Client-side validation rejects the response; the module cannot render. | Same underlying cause as PD-01 — return the documented pillar values.
KE-02 | KPI Explorer | Medium | KPI records have no formula, baseline, target or source institution | GET /kpi-explorer/kpis/:id returns null for all four fields on every KPI checked. | A figure cannot be checked against its target or attributed to a responsible institution. | Populate per API.md's KPI profile contract.
KE-03 | KPI Explorer | Medium | History points carry no link back to a submission | Each history entry's submissionId is null. | A published figure cannot be traced back to the return that produced it. | Link each history point to its originating submission.
KE-04 | KPI Explorer | High | KPI Explorer values match the unchanging Executive Overview figures exactly | Every KPI value checked here is identical to its Executive Overview counterpart (EO-01), while carrying no formula, baseline, target or submission link (KE-02, KE-03). For Metering Rate and ATC&C Loss Rate specifically, the NERC dataset needed to calculate both was provided and a real submission of it already exists in the queue (see DS-01). | For the two KPIs backed by data already provided, these figures cannot be confirmed as calculated rather than a placeholder pending the ingestion pipeline. | For Metering Rate and ATC&C Loss Rate: confirm the calculation path from the provided NERC data. For the remaining KPIs: we will provide source data as it becomes available.
KE-05 | KPI Explorer | Low | Published figures are roughly a year older than their last-updated date | One KPI shows reportingPeriod "Q3 2025" against a lastUpdated roughly a year later, checked against today's date. | The dashboard may present outdated figures as current. | Confirm the reporting cycle these figures are meant to be on.
RP-01 | Reports | Medium | Reports do not appear to be built from current records | lastUpdated on this response has not changed across repeated calls over several hours, matching the same pattern as Executive Overview (EO-01). | A generated report may not reconcile with what the dashboard currently shows. | Confirm reports are generated from live records at request time.
RP-03 | Reports | Low | Most report filter lists offer only one option | GET /reports/filters returns a single entry for period, pillar, state, DisCo, programme/agency, validation status and readiness tier. | These filters cannot express a real selection yet. | Populate from the same reference data used elsewhere on the platform.
BR-01 | Branding | Low | Branding configuration does not appear to change between requests | lastUpdated on this response has not changed across repeated calls, same pattern as EO-01. | Configuration changes may not be durably saved. | Confirm branding writes persist and are reflected on the next read.
SE-01 | Authorization | Critical | Server-side role and scope checks are not yet confirmed | The login response returns the user's role as a label but no permission set or institution/geography scope. This matches Open Question 9 already recorded in API.md: role enforcement is currently client-side only. | If unresolved, any authenticated account may be able to reach data or actions outside its intended role. | Confirm each endpoint checks the caller's role and scope server-side, per API.md Open Question 9.
SE-02 | Authorization | Medium | Not yet tested with a non-administrator account | This review had access to one System Administrator credential only, so role-scoped access could not be exercised end-to-end. | SE-01 cannot be confirmed resolved without this test. | Provide a second test account with a non-administrator role so this can be verified.
SE-03 | API design | Low | Requests to non-existent paths return 401 rather than 404 | A request to a path that matches no route at all returns 401 when unauthenticated. The same request with a valid session correctly returns 404 "No route matches" (used as evidence throughout this register). | Without a valid session, a client cannot distinguish a protected route from one that does not exist, which makes integration and troubleshooting slower than necessary. | Consider returning 404 for unmatched paths regardless of authentication state.
XC-01 | Reference data | Medium | The institution list includes entries unrelated to Mission 300 | GET /api/filters and GET /api/stakeholders both return three institutions with health/education/works mandates (e.g. "National health policy and PHC oversight") alongside the DisCos and TCN that belong to the energy sector. | Selecting these in a filter, or seeing them in the Stakeholders directory, does not correspond to anything in the Compact. | Confirm whether these should be removed from the Mission 300 institution list.
XC-02 | State & DisCo | Medium | State-level comparison data is limited | GET /state-disco/comparison currently returns two rows. | State-level performance views cannot yet show a national picture. | Confirm the plan for populating this across all reporting states.
XC-03 | Public Gateway | Low | The public overview endpoint does not respond to filters | GET /api/public/overview returns an identical response regardless of the pillar or institution parameters supplied, though it is correctly public and cacheable. | A visitor cannot narrow this view before signing in. | Apply filters here consistent with the rest of the platform, once EO-02/EO-03 are resolved.

## Endpoint Inventory
Method | Endpoint | Observed status | Behaviour | Note
GET | /api/executive-overview | 200 | Does not change between calls | See EO-01
GET | /api/public/overview | 200 | Public, cacheable | Does not respond to filters — XC-03
GET | /api/filters | 200 | Responds to inspection
GET | /api/branding | 200 | Does not change between calls | See BR-01
GET | /api/kpi-explorer | 200 | Responds to inspection | pillar returned as integer — KE-01
GET | /api/kpi-explorer/filters | 200 | Responds to inspection
GET | /api/kpi-explorer/kpis/:id | 200 | Responds to inspection | formula/baseline/target null — KE-02
GET | /api/pillars/:pillar | 404 | Not reachable with documented value | See PD-01
GET | /api/programs | 200 | Responds to inspection
GET | /api/programs/filters | 200 | Responds to inspection
POST | /api/programs | not yet added | Not yet in contract | See new sheet
POST | /api/programs/projects | not yet added | Not yet in contract | See new sheet
PATCH | /api/programs/projects/:id | not yet added | Not yet in contract | See new sheet
DELETE | /api/programs/projects/:id | not yet added | Not yet in contract | See new sheet
GET | /api/bottlenecks | 200 | Responds to inspection
GET | /api/bottlenecks/filters | 200 | Responds to inspection
GET | /api/stakeholders | 200 | Responds to inspection | See XC-01
GET | /api/administration | 200 | Responds to inspection
GET | /api/administration/filters | 200 | Responds to inspection
GET | /api/reports | 200 | Does not change between calls | See RP-01
GET | /api/reports/filters | 200 | Mostly single-option lists | See RP-03
GET | /api/reports/methodology | 404 | Not yet in contract | See new sheet
POST | /api/branding/reset | 404 | Not yet in contract | See new sheet
GET | /api/state-disco/filters | 200 | Responds to inspection
GET | /api/state-disco/states | 200 | Responds to inspection
GET | /api/state-disco/overview | 200 | Responds to inspection
GET | /api/state-disco/comparison | 200 | Two rows | See XC-02
GET | /api/state-disco/delivery | 200 | Responds to inspection
GET | /api/state-disco/supply-tariff | 200 | Responds to inspection
GET | /api/data-submissions/filters | 200 | Responds to inspection
GET | /api/data-submissions/datasets | 404 | Not yet in contract | See new sheet
GET | /api/data-submissions/obligations | 200 | Due labels inconsistent with due dates | See DS-06
GET | /api/data-submissions/submissions | 200 | Responds to inspection
GET | /api/data-submissions/validation | 200 | Responds to inspection
GET | /api/data-submissions/validation/:id | 200 | issues always empty in sample checked | See DS-02
POST | /api/data-submissions/obligations/:id/upload | 201 | Extracted value not tied to content | See DS-01
POST | /api/data-submissions/validation/:id/decisions | not tested | — | See DS-03
GET | /api/data-submissions/templates/:fileName | 200 | Not spreadsheet-format content | See DS-04
GET | /api/data-submissions/overdue | 200 | Contains a not-yet-due obligation | See DS-06
GET | /api/data-submissions/gaps | 200 | Responds to inspection

## Contract Updates Needed
Method | Endpoint | What it does | Used by | Why it is not in the contract yet
POST | /programs | Create a programme | Add Programme page | Not specified in any version of the contract. The current contract only documents GET routes for Programmes, and notes there is deliberately no write path yet.
POST | /programs/projects | Create a project | Add Project page | Same as above — no write path documented for Projects.
PATCH | /programs/projects/:id | Edit a project | Edit Project page | Same as above.
DELETE | /programs/projects/:id | Delete a project | Project actions menu | Same as above.
PATCH | /kpi-explorer/kpis/:id/active | Activate or deactivate a KPI | KPI Explorer admin action | Distinct from the documented PATCH /kpi-explorer/kpis/:id (which updates metadata). This one toggles active status and has not been specified separately.
GET | /data-submissions/datasets | Dataset catalogue | Data Submissions overview | Not in the contract. Added to the frontend after the last handoff.
GET | /reports/methodology | Report methodology panel | Reports page | Not in the contract. Added to the frontend after the last handoff.
POST | /branding/reset | Reset branding to default | Administration → Customization | Not in the contract. Added to the frontend after the last handoff.

## Questions for Backend Team
# | Question | Response | Date
1 | Which modules are considered production-ready today, and which are known placeholders?
2 | For a given displayed KPI figure, what is the intended source: a specific accepted submission, an approved public figure, or something else — and how would we trace one back to the other?
3 | /api/pillars/:pillar currently accepts integers; API.md specifies the six named pillar values. Which side should change?
4 | Executive Overview does not appear to respond to the pillar or period filters (EO-02, EO-03). What is the plan and timeline to align with API.md's filter contract?
5 | Uploading a populated file to Data Submissions returns the same extracted value regardless of content (DS-01). What is the status of file parsing and calculation on that path?
6 | Can we get a second test account with a non-administrator role, to verify role-scoped access end-to-end?
7 | Obligation due/overdue labels do not appear to reflect the due date (DS-06). What computes these today?
8 | Downloaded templates are not in spreadsheet format and do not carry identifying columns (DS-04, DS-05). When is this expected to align with API.md?
9 | The institution reference list includes entries outside the energy sector (XC-01). Should these be removed?
10 | What is the recommended way for us to confirm, end to end, that an approved submission updates the corresponding KPI record (DS-03)?
11 | See the Contract Updates Needed sheet — these were added to the frontend after the contract was last shared. When is a good time for us to walk through them together so we can specify each one properly before asking for it to be built?