## About
M300 Monitoring Platform | Backend gap register
Prepared | 25 August 2026
Backend reviewed | https://nigeria.geappindia.org/api
Method | Authenticated live probing as a System Administrator account, read-only GET requests, plus inspection of the backend route table and controllers. No writes were issued and no backend code or data was changed.
Scope | The whole dashboard, not only document upload.
How to read this | Gap Register lists every verified gap with the evidence that established it. Endpoint Inventory is the observed state of every route. Questions for Backend Team is the list requiring a written response.
Severity | Critical: the module reports results that are not true, or a security boundary is absent. High: a required capability is missing or a module cannot load. Medium: incorrect behaviour with a workaround. Low: cosmetic or configuration.
Note on evidence | Every row in Gap Register was verified directly. Where a claim could not be verified it is marked as such rather than asserted — see SE-02.
Counts | 46 gaps · 11 critical · 22 high · 9 medium · 4 low

## Gap Register
ID | Module | Severity | Gap | Evidence (verified) | Impact | Recommended fix | Owner | Target date | Status
DS-01 | Data Submission | Critical | Uploaded file is never parsed | POST /data-submissions/obligations/:id/upload reads only $_FILES["file"]["name"]. No spreadsheet or CSV parser exists anywhere in the backend (no PhpSpreadsheet, fgetcsv, str_getcsv, ZipArchive, simplexml; none in composer.json). | Any file of any type is accepted. The KPI value returned is the literal 57.4 written in the controller, regardless of content. | Parse the uploaded workbook/CSV server-side and derive the value from its rows.
DS-02 | Data Submission | Critical | Validation always reports success | automatedCheck=pass, issueCount=0, issues=[], validationSummary="Automated checks passed with 0 issues." are constants in the controller, not computed. | A custodian uploading an incorrect or corrupt return is told it passed. No one is alerted. | Implement field-level and business-rule validation; persist issues to validation_issue.
DS-03 | Data Submission | Critical | Approval publishes nothing | decide() sets $published = $s["extractedValues"] and returns it in the HTTP response. No database write occurs. Response message reads "Published to Metering Rate." | Approved figures never reach kpi_values or metric_observation. The platform reports a publication that did not happen. | Publish approved values transactionally into KPI history and link the accepted submission to the obligation.
DS-04 | Data Submission | Critical | Live proof: real NERC workbook returned the hardcoded value | Submission SUB-2026-0001 (uploaded 2026-08-25T07:23:38Z, fileName "Compiled NERC Data 2020 - 2026.xlsx") has extractedValues[0].value = 57.4. That workbook holds 721 metering rows across 11 DisCos, 2020-2026. | Genuine source data was submitted and the response was the constant from the source code. | Covered by DS-01. Re-run this submission once parsing exists and confirm the value changes.
DS-05 | Data Submission | High | submission and validation_issue tables are never used | Neither table appears in any FROM/JOIN/INTO/UPDATE across all controllers and repositories. Submissions are held in a JSON/file store. | No durable, queryable submission record; no immutable history; no lineage from a figure back to its return. | Move the submission pipeline onto the existing database tables.
DS-06 | Data Submission | High | Templates are CSV served as .xlsx | GET /data-submissions/templates/metering-performance-v3.xlsx returns 50 bytes beginning "mete" (6d 65 74 65) with Content-Type application/vnd.openxmlformats-officedocument.spreadsheetml.sheet. A real .xlsx is a ZIP beginning 50 4b 03 04. | Excel refuses or warns on the file. X-Content-Type-Options: nosniff prevents the browser correcting it. | Generate a real workbook from the dataset field definitions at download time.
DS-07 | Data Submission | High | Template columns cannot identify a row | The template header is: metered_customers, total_customers, reporting_notes. No DisCo, state or reporting-period column. | A completed return cannot be attributed to a utility or a quarter, so it cannot be validated or aggregated. | Derive template columns from dataset_field definitions, including all identifying fields.
DS-08 | Data Submission | High | Obligation due labels do not match their due dates | On 2026-08-25: OBL-2026-0021 dueDate 2026-10-15 labelled "Due in 5 days" (actually 51 days away). OBL-2026-0022 dueDate 2026-10-05 labelled "6 days overdue" (actually 41 days in the future). | OBL-2026-0022 also appears in /data-submissions/overdue. Compliance reports a breach six weeks before the deadline. | Compute due and overdue state from dueDate against the current date.
DS-09 | Data Submission | Medium | Actor identity is hardcoded | submittedBy is always "usr-006"; the decision actor recorded in history is always "usr-014"; reviewer is always "Grace Etim", assigned before any review. | The review trail names the wrong people. Accountability cannot be established. | Record the authenticated user on submission and on each decision.
DS-10 | Data Submission | Medium | extractedValues uses a foreign KPI id scheme | extractedValues[0].kpiId = "M300-P3-004", which is m300-demo-backend’s identifier format. This backend’s own kpi_definition uses integer ids, where Metering Rate is 8. | The extracted value references a KPI that does not exist in this system, so it could not be published even if DS-03 were fixed. | Use this system’s KPI identifiers, or agree one scheme across both backends.
DS-11 | Data Submission | Medium | GET /data-submissions/datasets returns 404 | Probed with a valid admin token: 404 {"message":"No route matches /api/data-submissions/datasets"}. The frontend calls this route. | The dataset catalogue cannot load. | Implement the route or remove the frontend call.
EO-01 | Executive Overview | Critical | All headline figures are hardcoded | Controller returns literal arrays. lastUpdated is the constant 2025-10-14T09:12:00Z rather than a query time. | The dashboard’s primary figures are not monitored results and never change. | Read the four outcomes from the KPI tables, which already hold these rows.
EO-02 | Executive Overview | Critical | Headline cards ignore the pillar filter | GET /executive-overview?pillar=clean-cooking returns identical headline values to the unfiltered call (137.3M, 70.0%, 5.4 GW, 26.0%), while nationalPerformance drops 6 to 0 and ongoingProjects 2 to 0. appliedPillar is echoed as "clean-cooking". | National totals are displayed under a pillar heading, and the response asserts the filter was applied. Worse than not filtering. | Apply every filter before computing each section, or return empty for a non-matching slice.
EO-03 | Executive Overview | Critical | reportingPeriod is ignored entirely | GET /executive-overview?reportingPeriod=2020-Q1 returns a byte-identical response to the unfiltered call. | No prior period can be viewed. A monitoring platform that cannot show history is not monitoring. | Filter observations by reporting period server-side.
EO-04 | Executive Overview | High | accessDelivery and exceptions ignore the pillar filter | Both remain at 3 and 1 rows respectively under ?pillar=clean-cooking. | Sections inconsistent with the rest of the filtered payload. | Apply the filter to every section.
CT-01 | Contract | High | cprTargets is absent from the payload | Frontend schema requires exactly 4 entries; the backend sends the field not at all. Verified by validating the payload against executiveOverviewSchema. | Response rejected at the client boundary unless the frontend defaults it. | Return the four CPR targets.
CT-02 | Contract | High | kpiId missing on all four headline cards | peopleWithElectricityAccess, accessRate, generationCapacity, cleanCookingAccess all omit kpiId. | KPI Explorer deep-links from the overview cards cannot work. | Include the backing KPI id, or null where a figure is composite.
CT-03 | Contract | High | milestones missing on compact outcome cards | Required array absent on peopleWithElectricityAccess and cleanCookingAccess. | Bullet charts cannot show interim checkpoints, so progress cannot be read against the approved trajectory. | Return approved milestones, or an empty array where none are defined.
CT-04 | Contract | High | history missing on nationalPerformance metrics | Required array absent on every metric. | No trend view on national performance rows; no evolution charts on the public gateway. | Return period-labelled history per metric.
CT-05 | Contract | High | sparkline sends bare numbers, not period-labelled points | accessRate.sparkline = [52.0, 55.0, 58.5, 61.0, 70.0]. Contract requires [{period, value}]. | No real time axis can be drawn; periods are unknown to the client. | Send {period, value} pairs.
CT-06 | Contract | Medium | ongoingProjects missing four required fields | leadName, comment, pipelineReadiness and statusHistory are all absent. | Project lead column blank; no status-evolution table; no pipeline readiness badge. | Return all four, using null/empty where genuinely unknown.
CT-07 | Contract | Medium | exceptions missing followUp | Required string absent on bottleneck exception rows. | The register cannot show what is being done about an unresolved exception. | Return the follow-up note.
PD-01 | Pillar Dashboard | Critical | Every pillar page returns 404 | GET /api/pillars/1, /2, /3 return 200. GET /api/pillars/clean-cooking and /generation-network return 404 "Unknown pillar". The frontend only ever requests the slug form. | The entire Pillar Dashboard module is unreachable, not partially working. | Accept the six pillar slugs at the API boundary and map them to internal ids.
KE-01 | KPI Explorer | Critical | pillar returned as an integer, violating the contract enum | GET /kpi-explorer returns {"id":"2","pillar":"2"}. pillarIdSchema is a closed enum of six slugs. | The client rejects the response with a contract error; KPI Explorer shows its error state. | Emit pillar slugs. Same root cause as PD-01.
KE-02 | KPI Explorer | High | KPI records carry no formula, baseline, target or source institution | GET /kpi-explorer/kpis/2 returns formula, baseline, target and sourceInstitution all null. | A figure cannot be reproduced, checked against its target, or attributed to a custodian. | Populate KPI metadata as first-class queryable columns.
KE-03 | KPI Explorer | High | KPI history has no submission lineage | history entries carry submissionId: null. | No figure can be traced back to the return that produced it. | Link each published observation to its accepted submission.
KE-04 | KPI Explorer | High | KPI values appear to be transcribed from the hardcoded controller values | Every KPI value matches its Executive Overview literal exactly (31.2, 57.4, 76.4, 27.4, 22.9, 5400MW, 26%, 137,300,000), while formula/baseline/target/submissionId are all null. | The database is a second copy of unsourced numbers rather than an independent, derived source of truth. | Derive values from accepted submissions; see the NERC workbook opportunity in the addendum.
KE-05 | KPI Explorer | Medium | Published figures are roughly a year stale | reportingPeriod "Q3 2025" against lastUpdated 2026-08-13, checked on 2026-08-25. | The dashboard presents year-old figures as current. | Establish a reporting cycle and surface the gap when a period is overdue.
PR-01 | Programmes & Projects | High | POST /api/programs does not exist | Absent from the route table. The frontend exposes an Add Programme page that calls it. | Creating a programme fails. | Implement with validation, authorization, history and audit — or hide the UI until ready.
PR-02 | Programmes & Projects | High | POST /api/programs/projects does not exist | Absent from the route table. The frontend exposes an Add Project page. | Creating a project fails. | As PR-01.
PR-03 | Programmes & Projects | High | PATCH /api/programs/projects/:projectId does not exist | Absent from the route table. The frontend exposes an Edit Project page. | Editing a project fails. | As PR-01.
PR-04 | Programmes & Projects | High | DELETE /api/programs/projects/:projectId does not exist | Absent from the route table. | Deleting a project fails. | As PR-01.
RP-01 | Reports | High | Reports are static and not built from live records | GET /reports returns lastUpdated 2025-10-14T09:12:00Z (the hardcoded constant). report_template, report_run and scheduled_report tables are never queried. | Reports do not reconcile to the dashboard and no run history exists. | Generate reports from accepted observations and implementation records.
RP-02 | Reports | Medium | GET /api/reports/methodology returns 404 | Probed with a valid admin token. The frontend calls this route. | Methodology panel cannot load. | Implement or remove the frontend call.
RP-03 | Reports | Low | Report filter lists contain a single option each | GET /reports/filters returns 1 option for periods, pillars, states, DisCos, programmes, validation statuses and readiness tiers. | Filters are placeholders and cannot express a real selection. | Populate from the same reference data the rest of the platform uses.
BR-01 | Branding | Low | Branding is static and file-persisted | GET /branding returns lastUpdated 2025-10-14T09:12:00Z. | Configuration changes are not durable in the database. | Persist branding in the database with admin-only writes.
BR-02 | Branding | Low | POST /api/branding/reset does not exist | Absent from the route table; the frontend calls it. | Reset action fails. | Implement or remove the frontend call.
SE-01 | Authorization | Critical | Login returns no permissions or scopes | Login payload is {accessToken, expiresAt, user:{id, name, email, role}}. role is a display string ("System Administrator"). No permission set, no institution or geography scope. | The server has no scope model to enforce and the client cannot enforce anything. Frontend navigation hiding is not a security boundary. | Return a permission and scope set, and authorize every request by action and scope.
SE-02 | Authorization | High | Server-side authorization is unverified | Only an administrator credential was available for this review, so the claim that a provider account can read Administration data could be neither confirmed nor refuted. | A security boundary is untested. | Provide a non-administrator test account. This is the highest-value outstanding test.
SE-03 | Authentication | Medium | User enumeration on /auth/identify | A registered address returns 200; an unregistered one returns 404 "We could not find an active account for that email." | An unauthenticated oracle for which addresses hold accounts on a government platform. | Return 200 in both cases and let the password step fail.
SE-04 | API design | Low | 401 is returned for routes that do not exist | GET /api/this-route-cannot-possibly-exist returns 401. The auth guard runs before the router. | An unauthenticated 401 does not distinguish "protected" from "absent", so the API cannot be enumerated or diagnosed without a token. | Route first, then authorize, so a missing route returns 404.
XC-01 | Audit | Critical | No action anywhere is audited | The audit_event table exists in the schema and is never written to by any controller or repository. | Uploads, decisions, approvals, edits, exports and administrative changes leave no immutable record. | Write audit events for every state-changing action and expose a cross-module activity API.
XC-02 | Schema | High | Twelve schema tables are never queried | Never referenced in any FROM/JOIN/INTO/UPDATE: submission, validation_issue, field_definition, evidence_document, audit_event, controlled_reference, access_scope, action, bottleneck_programme_link, report_template, report_run, scheduled_report. | The workflows those tables model — ingestion, validation, evidence, audit, scoping, reporting — are not implemented. | Use the tables the schema already defines rather than fixed arrays and file stores.
XC-03 | Deployment | High | Committed SQL does not match the deployed database | nigeria_m300_mysql.sql seeds Health, Education and Infrastructure pillars, an Under-5 Mortality Rate KPI and Ministries of Health/Education. The deployed database holds the six Compact pillars, 14 M300 KPIs and 18 real institutions. | The deployment is not reproducible and the production schema cannot be reviewed. | Commit the schema and seed that match production.
XC-04 | State & DisCo | High | State and DisCo responses are fixed arrays | Served from MockDb rather than metering, ATC&C, remittance or implementation records. /state-disco/comparison returns 2 rows. | State-level performance is not derived from submissions or observations. | Rebuild as queries over accepted observations.
XC-05 | Public Gateway | Medium | /api/public/overview ignores all parameters | Byte-identical across repeat calls and across ?pillar= and ?institution=. Correctly cacheable (public, max-age=60). | The public endpoint is static. | Serve publishable observations, and grow the payload so the public page can stop calling protected endpoints.

## Endpoint Inventory
Method | Endpoint | Observed | Backing | Note
GET | /api/executive-overview | 200 | Hardcoded | lastUpdated is the literal 2025-10-14T09:12:00Z
GET | /api/public/overview | 200 | Hardcoded | Public and cacheable; ignores all query parameters
GET | /api/filters | 200 | Live
GET | /api/branding | 200 | Hardcoded | lastUpdated 2025-10-14T09:12:00Z
GET | /api/kpi-explorer | 200 | Live | Returns integer pillar ids; violates the contract enum
GET | /api/kpi-explorer/filters | 200 | Live
GET | /api/kpi-explorer/kpis/:id | 200 | Live | formula, baseline, target, sourceInstitution all null
GET | /api/pillars/:pillar | 404 | Broken | Accepts integer ids only; the frontend sends slugs
GET | /api/programs | 200 | Live
GET | /api/programs/filters | 200 | Live
POST | /api/programs | absent | Missing | Frontend Add Programme page calls this
POST | /api/programs/projects | absent | Missing | Frontend Add Project page calls this
PATCH | /api/programs/projects/:id | absent | Missing | Frontend Edit Project page calls this
DELETE | /api/programs/projects/:id | absent | Missing
GET | /api/bottlenecks | 200 | Live
GET | /api/bottlenecks/filters | 200 | Live
GET | /api/stakeholders | 200 | Live
GET | /api/administration | 200 | Live | Readable by any authenticated account
GET | /api/administration/filters | 200 | Live
GET | /api/reports | 200 | Hardcoded | lastUpdated 2025-10-14T09:12:00Z
GET | /api/reports/filters | 200 | Hardcoded | One option per filter
GET | /api/reports/methodology | 404 | Missing | Frontend calls this route
POST | /api/branding/reset | absent | Missing | Frontend calls this route
GET | /api/state-disco/filters | 200 | Mock
GET | /api/state-disco/states | 200 | Mock
GET | /api/state-disco/overview | 200 | Mock
GET | /api/state-disco/comparison | 200 | Mock | Two rows
GET | /api/state-disco/delivery | 200 | Mock
GET | /api/state-disco/supply-tariff | 200 | Mock
GET | /api/data-submissions/filters | 200 | Fixed
GET | /api/data-submissions/datasets | 404 | Missing | Frontend calls this route
GET | /api/data-submissions/obligations | 200 | Fixed | Due labels do not match due dates
GET | /api/data-submissions/submissions | 200 | File store
GET | /api/data-submissions/validation | 200 | File store
GET | /api/data-submissions/validation/:id | 200 | File store | issues always empty
POST | /api/data-submissions/obligations/:id/upload | 200 | Stub | File never parsed; returns hardcoded 57.4
POST | /api/data-submissions/validation/:id/decisions | 200 | Stub | Publishes nothing to the database
GET | /api/data-submissions/templates/:fileName | 200 | Stub | 50-byte CSV served as .xlsx
GET | /api/data-submissions/overdue | 200 | Fixed | Lists an obligation 41 days before it is due
GET | /api/data-submissions/gaps | 200 | Fixed

## Questions for Backend Team
# | Question | Response | Date
1 | Provide the schema and seed that match the deployed database, under version control.
2 | /api/pillars/:pillar accepts integer ids; the frontend contract uses the six pillar slugs, so every Pillar Dashboard request 404s. Which side maps?
3 | Executive Overview headline cards do not respond to pillar, and reportingPeriod is ignored on every section. When will headline figures be derived per slice?
4 | KPI records carry no formula, baseline, target or sourceInstitution, and history rows carry submissionId: null. What produced these values, and what is the plan for lineage?
5 | Why does /auth/identify distinguish registered from unregistered emails?
6 | Provide a non-administrator test account so server-side authorization can be verified.
7 | POST /data-submissions/obligations/:id/upload never reads the uploaded file and returns a hardcoded 57.4 Metering Rate with issueCount 0 regardless of content. What is the plan and date for real parsing, validation and calculation?
8 | Approving a submission writes nothing to kpi_values or metric_observation, and the submission / validation_issue tables are unused. Where is an approved figure supposed to be persisted?
9 | Templates are served as 50-byte CSV headers with .xlsx filenames and XLSX MIME types, and carry no DisCo, state or period column. When will templates be generated from the dataset field definitions?
10 | Obligation due labels do not match their due dates — an obligation due 2026-10-05 was reported "6 days overdue" on 2026-08-25 and listed under /overdue. What computes these?
11 | Which modules are declared production-ready, and which are acknowledged representative implementations?
12 | For every displayed KPI, what exact observation, accepted submission, source reference and formula produced the value?
13 | What server-side permission and scope rule protects each endpoint?
14 | Which audit events are written for login, upload, edit, validation, approval, export and administration?