Design and Implementation of the M300 Implementation Monitoring Dashboard for Nigeria

Inception Report

For

April 2026

Energy Market and Rates Consultants Limited

Suite 217-219, Plot 1099

Adamawa Plaza

Central Business District

Abuja, FCT

E: mail@energy-mrc.com

W: www.energy-mrc.com

www.energy-mrc.com

# Table of Contents

Acronyms	1

1	Executive Summary	2

1.1	Purpose of the Assignment	2

1.2	Scope of Work	2

1.3	Implementation Structure	3

1.4	Key Deliverables	5

1.5	Timeline	7

1.6	Key Implementation Risks and Mitigation Measures	8

2	Introduction	11

2.1	Mission 300 and the Nigeria National Energy Compact	11

2.2	Need for an Integrated Monitoring Architecture	11

2.3	Institutional and Governance Framework	12

3	Understanding of the Assignment	13

3.1	Nature of the Assignment	13

3.2	Monitoring Architecture Requirements	13

3.3	Data Integration and Governance Imperatives	13

3.4	Role Delineation and System Sustainability	14

4	Methodological Framework	15

4.1	Indicator and Monitoring Framework Definition	15

4.2	Structured Data Lifecycle Design	15

4.3	Data Source Mapping and Institutional Responsibility Alignment	15

4.4	Dashboard Specification and Configuration Support	16

4.5	Validation, Testing, and Institutional Embedding	16

5	Detailed Scope of Work by Workstream	17

5.1	Workstream 1: Inception and Data Landscape Alignment	17

5.2	Workstream 2: Data Requirement Definition and KPI Structuring	17

5.3	Workstream 3: Data Source Mapping and Stakeholder Engagement	17

5.4	Workstream 4: Project Assessment and Performance Tracking	18

5.5	Workstream 5: Data Ingestion Design, Validation, and Governance	18

5.6	Workstream 6: Data Integration and Dashboard Configuration Support	19

5.7	Workstream 7: Capacity Building, Documentation, and Transition	19

6	Preliminary Baseline Assessment	20

6.1	Pillar 1: Rehabilitation and Expansion of Energy Infrastructure	20

6.2	Pillar 2: Ensuring Last Mile Access	20

6.3	Pillar 3: Ensuring Financially Viable Utilities	21

6.4	Pillar 4: Incentivizing Private Sector Participation	21

6.5	Pillar 5: Leveraging Regional Integration	21

6.6	Clean Cooking Baseline (Cross-Cutting Access Indicator)	22

7	Monitoring and KPI Framework Structure	23

7.1	Indicator Classification Structure	23

7.2	Indicator Typology	24

7.3	Indicator Definition and Traceability	24

7.4	Aggregation Structure	24

7.5	Reporting Cycles	25

7.6	Preliminary Validation Status and Known Data Constraints	25

8	Data Architecture and Validation Framework	26

8.1	Data Source Architecture	26

8.2	Data Flow Structure	27

8.3	Data Validation Principles	27

8.4	Reporting Frequency Alignment	27

8.5	Data Governance Considerations	27

8.6	Identified Data Constraints	27

# Acronyms

| Acronym | Definition |
| --- | --- |
| API | Application Programming Interface |
| CDMU | Compact Delivery Monitoring Unit |
| CSV | Comma-Separated Values |
| DisCos | Distribution Companies |
| EMRC | Energy Market and Rates Consultants |
| FMoF | Federal Ministry of Finance |
| FMoP | Federal Ministry of Power |
| GEAPP | Global Energy Alliance for People and Planet |
| GWh | Gigawatt-hour |
| KPI | Key Performance Indicator |
| LPG | Liquefied Petroleum Gas |
| M300 | Mission 300 |
| MTF | Multi-Tier Framework |
| MW | Megawatt |
| MYTO | Multi-Year Tariff Order |
| NBET | Nigerian Bulk Electricity Trading Plc |
| NDC | Nationally Determined Contribution |
| NERC | Nigerian Electricity Regulatory Commission |
| NGN | Nigerian Naira |
| Q2 | Quarter 2 |
| Q3 | Quarter 3 |
| REA | Rural Electrification Agency |
| SDG7 | Sustainable Development Goal 7 |
| TCN | Transmission Company of Nigeria |
| USD | United States Dollar |
| WAPP | West African Power Pool |
| API | Application Programming Interface |

# Executive Summary

## Purpose of the Assignment

The purpose of this assignment is to support the design and implementation of a structured, data-driven monitoring dashboard to track the progress of Mission 300 (M300) implementation in Nigeria.

The dashboard will serve as a centralized monitoring platform embedded within the Compact Delivery Monitoring Unit (CDMU), enabling the Federal Ministry of Power, the Federal Ministry of Finance, GEAPP, and other relevant stakeholders to track implementation progress across the five M300 pillars. The system will aggregate relevant datasets from public and private sector actors, support performance monitoring across ongoing and proposed interventions, and provide actionable insights for decision-making.

This assignment responds to the current absence of a unified monitoring system capable of consolidating sector-wide data related to electricity access, clean cooking, infrastructure rehabilitation, financial viability, private sector participation, and regional integration. The objective is to establish a coherent monitoring architecture that defines key performance indicators, structures data acquisition and validation processes, supports secure data aggregation, and enables interactive reporting through a configurable dashboard platform.

EMRC’s role under this assignment is to design the monitoring and data governance framework, define required datasets and reporting logic, support GEAPP in the configuration of the dashboard platform, and ensure that the system is sustainable through structured governance protocols, documentation validation, and capacity building for CDMU and relevant stakeholders.

The assignment will be implemented over a three-month period, followed by one month of post-implementation support to facilitate knowledge transfer, system stabilization, and institutional ownership.

## Scope of Work

The scope of this assignment covers the design and operationalization of a comprehensive monitoring framework and data aggregation structure to support the implementation of the M300 National Energy Compact for Nigeria. The work will be executed in close coordination with the Compact Delivery Monitoring Unit (CDMU), the Federal Ministry of Power, the Federal Ministry of Finance, and GEAPP’s technical team.

The assignment encompasses six core components.

Definition of Data Requirements and Key Performance Indicators: This includes identifying and structuring the datasets required to monitor M300 implementation across its five pillars, defining measurable indicators, establishing disaggregation levels, and aligning all metrics to Compact objectives and reporting needs.

Identification of Data Sources and Development of a Data Acquisition Strategy: This involves mapping primary and secondary data custodians across government institutions, utilities, private developers, and development partners; defining data collection frequency; and establishing protocols for data validation, integration, and quality assurance.

Project Assessment and Implementation Tracking: All ongoing and proposed sector projects relevant to M300 objectives will be reviewed and documented, including their timelines, budgets, objectives, and implementation status. Variances between planned and actual progress will be analyzed to support performance oversight.

Support to GEAPP in the Development of the Data Aggregation Platform: EMRC will define the monitoring architecture, data structuring logic, governance protocols, interoperability requirements, and reporting rules to ensure that the platform can securely collate, store, and analyze M300-related datasets. GEAPP will lead the technical configuration, system development, and hosting of the platform.

Dashboard Specification and Configuration Support: EMRC will define the dashboard requirements, including indicator groupings, user tiers, reporting frequencies, disaggregation levels, drilldown structures, visualization logic, and export formats. These specifications will guide GEAPP’s technical team in configuring the existing dashboard platform to meet M300 monitoring needs.

Capacity Building and Sustainability Support: This includes working alongside GEAPP to train CDMU and relevant stakeholders on dashboard usage, data input protocols, validation procedures, and governance processes. EMRC will validate technical documentation and user manuals to support long-term system sustainability and institutional ownership.

The scope of this assignment does not include independent development of the software platform. Technical system development, hosting, and software configuration will be undertaken by GEAPP, with EMRC providing structured advisory and configuration support.

## Implementation Structure

The assignment will be implemented over a three-month execution period, followed by one month of structured post-implementation support. The implementation will follow a milestone-driven structure aligned with deliverable submission, stakeholder validation, and platform configuration cycles.

The implementation will be organized around coordinated workstreams executed in parallel where appropriate, with defined review and validation checkpoints. The structure ensures that monitoring framework development, data governance design, and dashboard configuration support are sequenced logically and validated before final deployment.

The implementation structure consists of:

### Inception and Alignment Phase

- This phase confirms scope, reporting lines, stakeholder engagement framework, and implementation schedule. It establishes focal points within CDMU and relevant ministries and validates the detailed work plan.

### Technical Design Phase

- This phase focuses on developing the monitoring architecture, KPI framework, data governance structure, and reporting logic. Draft outputs are internally reviewed prior to stakeholder validation.

### Stakeholder Validation and Data Confirmation Phase

- During this phase, defined datasets, indicators, reporting frequencies, and governance protocols are validated with CDMU and relevant institutions. Data source confirmation and access pathways are formalized.

### Platform Configuration Support Phase

- GEAPP undertakes technical configuration of the dashboard platform based on the agreed specifications. EMRC provides structured configuration guidance and reviews outputs to ensure alignment with the defined monitoring architecture.

### System Validation and Deployment Phase

- Configured dashboards are tested against defined indicators and reporting logic. Any inconsistencies are resolved prior to final acceptance.

### Post-Implementation Support Phase

- Following deployment, EMRC will provide one month of support to stabilize reporting processes, address clarification requests, and ensure effective transfer of operational ownership to CDMU.

### Governance and Reporting

- A structured communication and reporting framework will be implemented to ensure effective coordination between EMRC, GEAPP, CDMU, and relevant stakeholders throughout the assignment.

- EMRC will maintain continuous coordination with GEAPP on technical delivery, including monitoring framework development, data structuring, and dashboard configuration support. GEAPP will serve as the primary coordination interface with CDMU and government stakeholders, ensuring alignment with institutional processes and facilitating access to relevant data custodians.

- Engagement with external stakeholders, including ministries, regulatory agencies, utilities, and development partners, will be conducted in a coordinated manner, with CDMU facilitating access and dissemination of technical outputs for review. EMRC will provide technical materials and respond to stakeholder inputs, while GEAPP will maintain visibility to ensure alignment.

- The assignment will follow a defined reporting cadence:

Bi-weekly coordination meetings will be held with CDMU, GEAPP, and EMRC to review progress, address issues, and align on next steps

Ad hoc technical sessions will be convened as required to address specific data, validation, or platform-related matters

Milestone-based review sessions will be conducted at key deliverable stages

- All deliverables will follow a structured review and validation process. Draft outputs will be submitted by EMRC to GEAPP and CDMU, after which CDMU will coordinate stakeholder review and consolidate feedback. Final outputs will be submitted following incorporation of validated inputs.

- An escalation mechanism will be applied where required. Issues related to delayed data access, stakeholder responsiveness, or inconsistencies in datasets will first be addressed through technical follow-up. Where necessary, escalation will be coordinated through GEAPP and CDMU to ensure timely resolution.

- This approach reflects the coordination structure agreed during the project kick-off, including bi-weekly follow-up sessions, CDMU-led stakeholder engagement, and ongoing coordination with GEAPP on platform-related activities.

## Key Deliverables

This assignment will produce a series of structured deliverables aligned with the workstreams outlined in the technical proposal. These deliverables will collectively establish the monitoring architecture required to track implementation of the Mission 300 National Energy Compact in Nigeria.

The Inception Report constitutes the first formal deliverable and establishes the implementation roadmap for the assignment.

Inception Report

- This document confirms the scope of work, implementation methodology, stakeholder engagement approach, coordination arrangements, reporting cadence, access roles, and sequencing of activities. It also provides a preliminary baseline assessment and outlines the framework through which subsequent technical deliverables will be developed.

Data Requirement Report

- Following approval of the Inception Report, EMRC will develop a comprehensive Data Requirement Report defining the datasets and key performance indicators required to monitor Mission 300 implementation. This report will specify indicator definitions, calculation logic, disaggregation levels, reporting frequencies, and alignment of indicators with the five pillars of the Nigeria National Energy Compact.

Data Source and Collection Strategy Report

- This report will establish the structured framework through which monitoring data will be obtained. It will include mapping of primary and secondary data sources, identification of institutional data custodians, definition of data access pathways, specification of reporting frequency, and documentation of data quality protocols. The report will also incorporate a consolidated Mission 300 project register and a summary of key implementation bottlenecks identified across ongoing and proposed interventions.

Prototype Dashboard

- Based on the defined data requirements and monitoring architecture, GEAPP’s technical team will configure an initial version of the monitoring dashboard on the existing platform. EMRC will support this process by providing indicator specifications, baseline datasets, and structured review feedback during testing and validation cycles.

Final Data Dashboard Monitoring System

Following validation of the prototype system, the final configured dashboard will be delivered with approved indicators, structured reporting views, user access controls, and visualization tools aligned with agreed monitoring requirements.

Training and Documentation Package

EMRC will support capacity building for the CDMU and relevant stakeholders through training sessions, operational guidance, and validation of technical documentation and user manuals prepared by GEAPP.

Final Report and Presentation

At the conclusion of the assignment, EMRC will deliver a consolidated final report summarizing implementation activities, monitoring architecture design, dashboard configuration outcomes, governance arrangements, and recommendations for sustaining the monitoring system

Post-Implementation Support

Following deployment of the monitoring system, EMRC will provide one month of post-implementation support to assist with system stabilization, clarification requests, and transition of operational ownership to CDMU.

## Timeline

The assignment will be implemented over a total duration of four months, consisting of three months of active implementation and one month of structured post-implementation support.

The schedule below presents the proposed implementation timeline, reflecting a phased but overlapping approach to stakeholder engagement, data collection, validation, and system configuration. Final milestone dates will be validated during the formal kick-off engagement with CDMU and GEAPP to ensure alignment with institutional availability and data access timelines.

Table 1: Implementation Milestone Matrix

| - Phase | - Key Activities | - Primary Outputs | - Target Completion |
| --- | --- | --- | --- |
| - Month 1 | - Inception and alignment activities | - Approved Inception Report | - End of Month 1 |
|  | - KPI definition and monitoring framework design | - Draft KPI Matrix |  |
|  | - Preliminary data source mapping and stakeholder identification | - Draft Data Source Map |  |
|  | - Stakeholder engagement initiation and baseline data collection (public and programme data) | - Initial baselube datasets and engagement structure |  |
|  | - Initial data requests to institutions and identification of reporting formats | - Data request templates and submission structure |  |
| - Month 2 | - Continued data collection from insitutional and public sources | - Consolidated dataset inputs | - End of Month 2 |
|  | - Data source validation and refinement of data source mapping | - Validated data source framework |  |
|  | - Finalization of data requirements and structuring | - Data Requirement Report |  |
|  | - Development of data source and collection strategy | - Development of data governance structure and validation protocols |  |
|  | - Project mapping and preliminary assessment | - Project register structuring and bottleneck analysis |  |
| - Month 3 | - Dashboard specification finalization | - Dashboard Specification Document | - Mid-Month 3 |
|  | - GEAPP configuration of prototype dashboard | - Prototype Dashboard |  |
|  | - Provision of structured data inputs and validation support | - Structured data inputs |  |
|  | - Dashboard validation and refinement | - Validated Dashboard System | - End of Month 3 |
|  | - Training and documentation validation | - Training and Documentation Package |  |
| - Month 4 | - Post-implementation support | - Stabilization Support and Final Handover | - End of Month 4 |
|  | - Final handover and operational transition | - Final Handover |  |

## Key Implementation Risks and Mitigation Measures

The successful delivery of the assignment is dependent on timely access to reliable data, effective stakeholder engagement, and alignment between defined indicators and available datasets. Based on the current understanding of the operating environment, several implementation risks have been identified, along with corresponding mitigation measures.

### Data Access Constraints

Access to institutional datasets may be delayed due to internal approval processes, data ownership considerations, or competing priorities within participating institutions.

Mitigation:
Early stakeholder engagement will be initiated during the inception phase to establish communication channels and identify focal points. Data requests will be issued early in the implementation period, and follow-up will be conducted through structured coordination with CDMU and GEAPP. Where delays persist, escalation will be undertaken through agreed coordination channels.

### Incompleter or Inconsistent Data

Datasets provided by different institutions may be incomplete, inconsistent, or not aligned with defined indicator requirements, particularly where data is not routinely standardized.

Mitigation:

Standardized data templates will be used to guide data submission, ensuring consistency in format and structure. Internal validation checks will be applied to identify inconsistencies, and targeted follow-up will be conducted to resolve gaps. Where necessary, proxy indicators or alternative data sources may be considered.

### Limited Availability of Disaggregated Data

Certain indicators may require disaggregated data (e.g., state-level or project-level data) that may not be readily available or systematically maintained.

Mitigation:
Indicator definitions will be aligned with available data where necessary, and data requirements will be refined during stakeholder validation. Supplementary datasets from publicly available sources and development partners will be used where appropriate to support indicator computation.

### Stakeholder Responsiveness and Coordination Challenges

Timely engagement with multiple stakeholders across ministries, agencies, and utilities may be affected by scheduling constraints and competing institutional priorities.

Mitigation:

A structured reporting cadence, including bi-weekly coordination meetings, will be maintained to ensure regular engagement. CDMU will support coordination and facilitate access to stakeholders, while GEAPP will maintain oversight to ensure alignment and timely resolution of engagement challenges.

### Alignment Between Data Availability and KPI Requirements

Some indicators defined within the monitoring framework may not be fully supported by available datasets at the required level of detail or reporting frequency.

Mitigation:

Indicator definitions will be reviewed and validated in consultation with stakeholders to ensure feasibility. Where necessary, indicators will be refined to reflect practical data availability, while maintaining alignment with overall monitoring objectives.

### Integration and Validation Risks

Delays or inconsistencies in data validation may affect the timely configuration and testing of the dashboard system.

Mitigation:

Data validation will be conducted progressively throughout the implementation period, rather than as a single-stage activity. Structured data inputs will be provided to GEAPP to support configuration, and iterative review of dashboard outputs will be undertaken to resolve inconsistencies prior to final deployment.

figure 1: Operational Sequencing

# Introduction

## Mission 300 and the Nigeria National Energy Compact

Mission 300 (M300) seeks to connect 300 million people in Sub-Saharan Africa to electricity by 2030 through coordinated sector reform, infrastructure investment, and private sector mobilization. Nigeria’s National Energy Compact operationalizes this objective at country level, setting measurable acceleration targets for electricity access and clean cooking.

As of 2022, Nigeria’s electricity access rate stood at 61 percent, leaving over 86 million people without access1. Clean cooking access was reported at 26 percent, with over 160 million people lacking modern cooking solutions2. In addition, an estimated metering gap of approximately 7 million electricity end users has been identified2.

These figures highlight both the scale of the access deficit and the structural complexity of delivery. The Compact’s ambition to accelerate electricity access growth from 4 percent to 9 percent annually2, and clean cooking access from 22 percent to 25 percent annually, requires disciplined monitoring of infrastructure expansion, financial sustainability, project execution, and private sector participation across multiple institutions.

The Compact is structured around five pillars: infrastructure rehabilitation and expansion; last mile access; financially viable utilities; private sector mobilization; and regional integration2.

Each pillar involves distinct datasets, implementing entities, and reporting streams. Without an integrated monitoring structure, tracking cross-pillar progress becomes fragmented and inconsistent.

## Need for an Integrated Monitoring Architecture

At present, datasets relevant to M300 implementation are distributed across ministries, regulatory agencies, utilities, development partners, and project developers. While individual institutions maintain operational data, there is no unified system that consolidates performance indicators across the five Compact pillars into a single monitoring framework.

This fragmentation creates three structural risks:

First, inconsistent definitions and reporting frequencies can limit comparability across datasets.

Second, delays in data validation can undermine timely decision-making.

Third, absence of centralized aggregation reduces visibility over implementation gaps, milestone slippages, and cross-pillar dependencies.

To address this, the Federal Ministry of Power and the Federal Ministry of Finance, working alongside GEAPP, have initiated the development of a centralized monitoring dashboard embedded within the Compact Delivery Monitoring Unit (CDMU). The dashboard will serve as the institutional mechanism for aggregating datasets, standardizing indicators, tracking project performance, and enabling structured reporting to stakeholders.

## Institutional and Governance Framework

The monitoring dashboard will be embedded within CDMU, which serves as the coordination platform for Compact implementation monitoring. The Consultant will report to the Federal Ministry of Power and the Federal Ministry of Finance and will work closely with CDMU and GEAPP throughout the assignment.

GEAPP will configure the technical dashboard platform, while EMRC will define the monitoring architecture, data requirements, governance framework, and reporting logic that will guide configuration and system operation. This division of roles ensures that technical deployment is anchored in a clearly defined monitoring structure and institutional governance framework.

The objective is not merely to deploy a digital interface, but to establish a structured monitoring system that supports accountability, cross-pillar coordination, and evidence-based policy oversight under the M300 Compact.

# Understanding of the Assignment

## Nature of the Assignment

The assignment is not limited to the development of a visual dashboard interface. It requires the design of a structured monitoring architecture capable of aggregating, validating, and reporting data across the five pillars of the M300 National Energy Compact.

The central challenge addressed by this assignment is the integration of heterogeneous datasets originating from multiple institutions, each operating under distinct reporting formats, validation standards, and operational timelines. Effective monitoring under M300 therefore depends on three interrelated components:

A clearly defined indicator framework aligned to Compact objectives

A structured data lifecycle model governing acquisition, validation, aggregation, and reporting

A configuration-ready dashboard specification that translates monitoring logic into operational views

The assignment requires aligning these components within an institutional framework embedded in CDMU and supported by GEAPP’s existing technical platform.

## Monitoring Architecture Requirements

Monitoring M300 implementation requires a layered structure that connects national-level targets to project-level execution. The monitoring architecture must therefore:

Map indicators to each of the five Compact pillars

Define measurable KPIs with consistent technical definitions

Establish disaggregation levels, including national, state, utility, and project-level reporting where applicable

Define reporting frequencies and validation timelines

Ensure traceability between reported figures and source datasets

The architecture must also accommodate both infrastructure indicators, such as connections and metering deployment, and institutional indicators, such as financial viability and private sector participation.

## Data Integration and Governance Imperatives

Data relevant to M300 implementation is distributed across ministries, regulatory agencies, utilities, project developers, and development partners. Integrating these datasets requires structured governance protocols to ensure:

Consistent data definitions

Quality assurance and validation checks

Clear data ownership and submission responsibilities

Defined update cycles

Escalation pathways for discrepancies

- Without these governance mechanisms, dashboard outputs risk becoming inconsistent or outdated, undermining credibility and policy usefulness.

- The assignment therefore requires not only the identification of datasets but also the establishment of a governance model that defines how data flows into the system, how it is verified, and how it is maintained over time.

## Role Delineation and System Sustainability

Under the agreed structure, GEAPP will configure and host the dashboard platform. EMRC’s role is to design the monitoring framework, define data requirements, establish governance protocols, and provide configuration guidance to ensure that the platform reflects the agreed monitoring architecture.

This delineation ensures that technical system development is grounded in a structured monitoring logic and institutional ownership model. The sustainability of the dashboard will depend on the clarity of data governance arrangements, the quality of documentation, and the capacity of CDMU and relevant stakeholders to maintain and update the system.

Accordingly, this assignment must result in both a functional monitoring dashboard and a clearly defined institutional framework for its continued operation.

# Methodological Framework

The methodological framework for this assignment translates the monitoring architecture and data governance approach outlined in EMRC’s technical proposal into a structured implementation sequence. The approach is designed to ensure that indicator definition, data structuring, governance protocols, and dashboard configuration support are logically aligned and validated prior to system deployment.

The methodology is organized around five execution components.

## Indicator and Monitoring Framework Definition

The first step of implementation will focus on defining the monitoring framework required to track M300 implementation across its five pillars.

This will involve:

Translating Compact objectives into measurable performance indicators

Defining technical calculation logic for each KPI

Establishing disaggregation levels required for reporting

Aligning indicators with reporting frequency requirements

Defining traceability between reported outputs and source datasets

This step ensures that the dashboard is built on defined measurement logic rather than aggregated figures without consistent definitions.

## Structured Data Lifecycle Design

This component will establish:

Data submission structures and required formats

Validation rules and quality control checks

Update cycles and reporting intervals

Version control requirements

Escalation protocols for discrepancies

- The objective is to ensure consistency between institutional data submissions and dashboard outputs.

## Data Source Mapping and Institutional Responsibility Alignment

Given that M300 implementation spans multiple institutions, systematic data source mapping will be undertaken to define reporting responsibility and access pathways.

This will include:

Identification of primary data custodians for each indicator

Confirmation of reporting mandates where applicable

Mapping of data submission frequency

Clarification of ownership and update responsibility

- This step establishes accountability within the monitoring system and reduces ambiguity over data provenance.

## Dashboard Specification and Configuration Support

Based on the defined monitoring framework and data lifecycle model, EMRC will prepare a structured dashboard specification document.

The specification will define:

Indicator groupings by pillar

Aggregation logic and calculation dependencies

Drilldown hierarchies

User access tiers

Reporting formats and export structures

GEAPP will configure the dashboard platform in accordance with this specification. EMRC will review configured outputs to verify alignment with agreed definitions, reporting logic, and governance protocols.

## Validation, Testing, and Institutional Embedding

Prior to deployment, configured dashboard outputs will undergo structured validation against defined indicators and reporting requirements.

This stage will include:

Technical review sessions with CDMU

Validation of data aggregation logic

Testing of user access tiers

Review of documentation and operating guidelines

Training sessions for relevant stakeholders

The objective is to ensure that the system is not only functional but institutionally embedded and operationally sustainable.

This methodological structure ensures that:

Monitoring logic is defined before configuration.

Data governance precedes aggregation.

Institutional roles are clarified before reporting.

Deployment follows validation.

# Detailed Scope of Work by Workstream

The assignment will be implemented through a series of structured workstreams that reflect the logical sequence required to establish the Mission 300 Monitoring Dashboard and its supporting data architecture. Each workstream corresponds to a defined component of the technical proposal and contributes to the development of a structured monitoring system embedded within the CDMU

## Workstream 1: Inception and Data Landscape Alignment

| - Component | - Description |
| --- | --- |
| - Objective | - Establish alignment with CDMU, the Federal Ministry of Power, the Federal Ministry of Finance, and GEAPP regarding the monitoring objectives, implementation approach, and data landscape relevant to Mission 300 implementation. |
| - Key Activities | - Confirm scope of work and reporting structure. Conduct preliminary review of the existing data landscape across relevant institutions. Identify key stakeholders involved in the production, management, and publication of sector datasets. Establish coordination arrangements, reporting cadence, and sign-off mechanisms for subsequent deliverables. |
| - Outputs | - Inception Report. |
| - Institutional Interface | - CDMU, Federal Ministry of Power, Federal Ministry of Finance, GEAPP. |

## Workstream 2: Data Requirement Definition and KPI Structuring

| - Component | - Description |
| --- | --- |
| - Objective | - Define the datasets and associated indicators required to monitor Mission 300 implementation across the five pillars of the Nigeria National Energy Compact. |
| - Key Activities | - Translate Compact objectives into measurable indicators. Define technical indicator definitions and calculation logic. Establish appropriate levels of disaggregation for reporting. Determine reporting frequency for each dataset. Structure the monitoring framework that will underpin the dashboard architecture. |
| - Outputs | - Data Requirement Report. |
| - Institutional Interface | - CDMU, Federal Ministry of Power, Federal Ministry of Finance, GEAPP. |

## Workstream 3: Data Source Mapping and Stakeholder Engagement

| - Component | - Description |
| --- | --- |
| - Objective | - Identify and map the institutional sources from which monitoring data will be obtained and establish structured data acquisition pathways. |
| - Key Activities | - Map data sources across ministries, regulatory agencies, utilities, project developers, development partners, and other stakeholders. Assess data availability, reporting frequency, format consistency, ownership, and access pathways for each source. Identify potential gaps, overlaps, and risks affecting data quality and completeness. Define appropriate data submission pathways based on the capacity of each reporting institution. |
| - Outputs | - Draft Data Source and Collection Strategy Report. |
| - Institutional Interface | - CDMU, GEAPP, relevant MDAs, utilities, development partners, and project implementers. |

## Workstream 4: Project Assessment and Performance Tracking

| - Component | - Description |
| --- | --- |
| - Objective | - Establish a structured basis for tracking Mission 300 implementation activities and identifying delivery constraints across relevant projects and programs. |
| - Key Activities | - Review and document active and proposed projects contributing to Mission 300 objectives. Develop a consolidated project template with standardized tracking fields, including location, implementing entities, timelines, and implementation stage classifications. Identify delivery bottlenecks through analysis of planned versus reported project progress. Define minimum reporting fields required for consistent project tracking. |
| - Outputs | - Mission 300 Project Register and summary of implementation bottlenecks integrated into the Data Source and Collection Strategy Report. |
| - Institutional Interface | - CDMU, Federal Ministry of Power, relevant implementing agencies, development partners, and project sponsors. |

## Workstream 5: Data Ingestion Design, Validation, and Governance

| - Component | - Description |
| --- | --- |
| - Objective | - Define the structured processes through which monitoring data will move from source institutions to the dashboard environment in a controlled and repeatable manner. |
| - Key Activities | - Design data ingestion workflows consistent with GEAPP’s platform architecture. Define validation rules, consistency checks, and exception handling procedures. Develop standardized data submission templates to facilitate reporting. Establish review and approval workflows to support traceability and accountability. Define governance roles and escalation pathways for unresolved data quality issues or delayed submissions. |
| - Outputs | - Final Data Source and Collection Strategy Report (building on the draft developed under Workstream 3), incorporating data submission templates, validation protocols, exception handling procedures, and governance arrangements. |
| - Institutional Interface | - CDMU, GEAPP technical team, relevant data custodians. |

## Workstream 6: Data Integration and Dashboard Configuration Support

| - Component | - Description |
| --- | --- |
| - Objective | - Support GEAPP’s technical team in configuring the monitoring dashboard based on the defined data requirements, monitoring framework, and reporting architecture. |
| - Key Activities | - Provide indicator specifications, baseline datasets, and reporting structures required for dashboard configuration. Review configured dashboard outputs to ensure alignment with defined indicators and aggregation logic. Support testing and validation cycles prior to final system deployment. |
| - Outputs | - Prototype Dashboard and Final Data Dashboard Monitoring System configured on GEAPP’s platform. |
| - Institutional Interface | - GEAPP technical team, CDMU. |

## Workstream 7: Capacity Building, Documentation, and Transition

| - Component | - Description |
| --- | --- |
| - Objective | - Ensure institutional ownership and sustainability of the monitoring system within CDMU and relevant government institutions. |
| - Key Activities | - Conduct training sessions for dashboard users and relevant stakeholders. Review and validate technical documentation and user manuals prepared for the system. Provide operational guidance for ongoing data reporting, validation, and dashboard management. Support transition of system operation to CDMU following deployment. |
| - Outputs | - Training and Documentation Package, Final Report and Presentation, and Post-Implementation Support. |
| - Institutional Interface | - CDMU, Federal Ministry of Power, Federal Ministry of Finance, GEAPP, and relevant stakeholders. |

# Preliminary Baseline Assessment

Baseline figures presented below are drawn from the most recent publicly available and verifiable sources, including the Nigeria National Energy Compact (2025), NERC Quarterly Reports (Q3 2025), SDG7 Tracking, and related official publications. As data availability varies by dataset, baseline reference years span 2022 to 2025 depending on the most recent validated source.

## Pillar 1: Rehabilitation and Expansion of Energy Infrastructure

As of 2025/Q3, the average available generation capacity of grid-connected power plants stood at 5,430.34 MW. Total electricity generated during the quarter was 9,227.56 GWh3.

Hydropower contributed 32.43 percent of total generation in Q3 2025 (2,992.76 GWh out of 9,227.57 GWh)3, reflecting seasonal improvements in hydro availability during the rainy season.

Sector performance remains constrained by Aggregate Technical, Commercial and Collection (ATC&C) losses. The weighted average ATC&C loss recorded across all DisCos in 2025/Q3 was 33.27 percent, comprising 17.31 percent technical and commercial losses and 19.30 percent collection losses3.

These figures highlight that while available capacity exceeds 5.4 GW, operational and commercial inefficiencies continue to limit effective energy delivery and financial sustainability.

## Pillar 2: Ensuring Last Mile Access

National electricity access was previously reported at 61 percent (2022), leaving over 86 million people without access to electricity2.

Off-grid deployment continues to complement grid expansion, with previously recorded figures of 107,519 household mini-grid connections and 14,326 SME connections (2024)2. In addition, approximately 2.93 million standalone solar home systems had been deployed as of 2024.

Despite these gains, significant access gaps remain, particularly in underserved and rural communities. The Multi-Tier Framework (MTF) survey currently covers only seven states (North-West zone), indicating that nationally representative service quality data remains incomplete.

## Pillar 3: Ensuring Financially Viable Utilities

As of 30 September 2025, there were 12,030,315 active registered electricity customers, of which 6,661,564 were metered, representing a metering rate of 55.37 percent3.

This implies approximately 5,368,751 unmetered active customers, indicating a substantial remaining metering gap.

Commercial performance indicators show that during 2025/Q3:

Total energy billed was ₦706.61 billion

Total revenue collected was ₦570.25 billion

Collection efficiency stood at 80.70 percent3

The weighted average ATC&C loss for the quarter was 33.27 percent, an improvement from 37.92 percent recorded in Q2 20253.

Upstream remittance performance to NBET and the Market Operator stood at 95.21 percent in Q3 20253.

In addition, the Federal Government assumed approximately ₦458.75 billion (about 59 percent) of generation costs in Q3 2025 through tariff subsidy support3.

While modest improvements are evident in billing and collection efficiencies, continued subsidy reliance underscores the need for sustained financial and operational reform under the Compact framework.

## Pillar 4: Incentivizing Private Sector Participation

The Compact establishes a target of mobilizing USD 15.5 billion in private capital for last-mile access by 20302. The baseline for private capital mobilized under the Compact framework remains recorded as USD 0 (2024), reflecting the starting point for structured tracking under M300.

Total investment required to achieve universal electricity access is estimated between USD 32.7–32.8 billion2.

Further validation is required to determine whether additional private capital mobilization figures exist outside the formal Compact tracking framework.

## Pillar 5: Leveraging Regional Integration

While the Compact identifies regional integration as a pillar, formalized baseline indicators directly measuring cross-border electricity trade volumes and interconnection utilization require further validation from system and market operators.

However, the Q3 2025 NERC report confirms that three international bilateral customers made cumulative payments of USD 7.125 million against USD 18.69 million invoiced during the quarter (38.09 percent remittance rate)3.

This confirms the existence of cross-border commercial transactions but indicates that structured baseline indicators for regional electricity exchange require further stakeholder confirmation.

## Clean Cooking Baseline (Cross-Cutting Access Indicator)

Clean cooking access previously stood at 26 percent (2024), leaving over 160 million people without access to modern cooking solutions2. Approximately 7.9 million households (10.5 percent) use LPG as their primary cooking fuel2, while electricity-based cooking remains limited at approximately 1 percent of households2.

Given the scale of the deficit, structured monitoring of clean cooking deployment and household transition metrics will be essential under the Compact framework.

# Monitoring and KPI Framework Structure

The Monitoring and KPI Framework establishes the structured logic through which M300 implementation will be tracked. The framework translates Compact objectives into measurable indicators and defines how these indicators are classified, organized, and reported within the monitoring system.

The full KPI Matrix is provided in Annex 1. This section outlines the structural logic underpinning that matrix.

## Indicator Classification Structure

The KPI Matrix is organized using a dual classification structure to ensure both analytical clarity and alignment with the M300 policy framework.

### Primary Classification – Thematic Categories

Indicators are grouped into operational categories reflecting sector structure and implementation areas. These include:

Metering

Grid Electricity Access

Mini-Grids

Standalone Solar (SHS)

Clean Cooking

Utility Performance and Losses

Generation and Transmission

Private Investment

Project Pipeline

Energy Access Quality (MTF)

Regional Integration

### Secondary Classification – Compact Pillar Alignment

Each indicator will also be mapped to one of the five pillars of the Nigeria National Energy Compact:

Pillar 1 – Infrastructure Rehabilitation and Expansion

Pillar 2 – Last Mile Access

Pillar 3 – Financially Viable Utilities

Pillar 4 – Private Sector Participation

Pillar 5 – Regional Integration

- This tagging enables filtering and aggregation of indicators by Compact pillar while preserving the thematic structure used for dashboard navigation.

## Indicator Typology

Indicators will be categorized by analytical function to distinguish between different types of monitoring metrics. Proposed indicator types include:

Output (e.g., number of connections, meters installed)

Outcome (e.g., access rates)

System Performance (e.g., ATC&C losses, collection efficiency)

Financial (e.g., tariff shortfall)

Investment (e.g., capital mobilization)

Capacity (e.g., installed or available generation capacity)

Pipeline (e.g., projects under development)

Access Quality (e.g., service tiers)

- This classification helps distinguish infrastructure deployment metrics from financial performance indicators and service quality metrics.

## Indicator Definition and Traceability

Each indicator within the monitoring framework will be defined using a standardized structure including:

A clear technical definition

Defined unit of measurement

Aggregation level

Reporting frequency

Identified data owner

Source reference

Validation status

- Where indicators are derived from underlying datasets, calculation logic will be documented to ensure transparency and consistency in reporting.

- This framework enables each metric displayed on the dashboard can be traced to a defined data source and calculation methodology.

## Aggregation Structure

- The monitoring framework is designed to support reporting across multiple geographic and institutional levels, subject to data availability.

National

DisCo-level

State-level

Project-level

- This layered aggregation framework enables both high-level Compact oversight and more granular operational diagnostics.

## Reporting Cycles

- Indicators will be aligned with the reporting cycle of their primary data sources. Depending on the dataset, reporting frequencies may include:

Monthly

Quarterly

Annual

Periodic (aligned to survey cycles)

- The dashboard will clearly display the reporting cycle associated with each metric to maintain temporal transparency.

## Preliminary Validation Status and Known Data Constraints

At the inception stage, several indicators have been provisionally identified but require further validation during stakeholder engagement and data confirmation processes.

Key constraints currently identified include:

Regional Integration Indicators

- Data on cross-border electricity flows and interconnection utilization requires confirmation through engagement with the Transmission Company of Nigeria and the West African Power Pool.

Private Capital Mobilization

Certain investment indicators require further clarification to distinguish between Compact-tracked capital and broader sector investment flows.

Project Pipeline Data

- Compilation of a comprehensive project register requires coordination with multiple implementing agencies and development partners

Energy Access Quality Data

- National coverage of Multi-Tier Framework service quality data remains incomplete.

- These issues will be addressed during the data sourcing and stakeholder engagement stages of implementation.

Data Governance Framework

- While indicators and data owners are defined, the formalized data submission and validation workflow will be developed in the subsequent Data Architecture and Governance section of this report.

# Data Architecture and Validation Framework

This section outlines the proposed data architecture through which datasets supporting the Mission 300 Monitoring Dashboard will be sourced, structured, validated, and integrated into the reporting environment. The objective is to ensure that all indicators presented within the dashboard are traceable to verified datasets and are updated in accordance with defined reporting cycles.

Detailed mapping of datasets, data custodians, and submission pathways will be documented in the Data Source and Collection Strategy Report. This section provides the structural logic that will guide the design of that framework.

## Data Source Architecture

The monitoring system will rely on multiple categories of sector data sources, corresponding to institutions responsible for producing operational, regulatory, and project-level information relevant to Mission 300 implementation.

At inception stage, three primary source categories have been identified:

### Publicly Published Sector Reports

This category includes regulatory publications, national policy documents, international tracking datasets, and development partner reporting platforms.

These sources provide foundational data for key indicators related to electricity access, utility performance, generation, and financial metrics. They are expected to form the initial basis for population of the monitoring system.

### Institutional Data Custodians

Certain indicators require engagement with institutions responsible for operational datasets that may not be publicly disaggregated.

Key institutional data custodians include transmission operators, electrification agencies, relevant government ministries, distribution companies, and development partners.

Data access pathways, reporting responsibilities, and submission mechanisms for these datasets will be defined during stakeholder engagement and formalized in the Data Source and Collection Strategy Report.

### Derived Indicators

Some KPIs are calculated from primary datasets rather than directly reported. These include indicators such as metering gap, tariff shortfall, renewable share in the generation mix, and population without access metrics.

The calculation logic for such indicators will be defined within the KPI Matrix and further formalized during implementation to ensure consistency and transparency.

## Data Flow Structure

The monitoring system will follow a structured data flow to ensure consistency between source datasets and dashboard outputs. This will include processes for data acquisition, standardization, validation, and integration.

The detailed data flow architecture, including ingestion pathways and system integration logic, will be defined in the Data Source and Collection Strategy Report.

## Data Validation Principles

To ensure reliability of reported indicators, the monitoring system will apply validation principles including source verification, consistency checks, and alignment with official reporting cycles.

Detailed validation rules, exception handling procedures, and approval workflows will be established as part of the Data Source and Collection Strategy Report.

## Reporting Frequency Alignment

Indicators will be aligned with the reporting cycles of their underlying data sources. These are expected to include monthly, quarterly, annual, and periodic reporting cycles depending on the nature of the dataset.

The monitoring system will clearly reflect the reporting frequency and reference period associated with each indicator to ensure transparency in interpretation and use.

## Data Governance Considerations

At inception stage, formalized data submission arrangements are not yet established. The monitoring architecture therefore assumes an initial reliance on publicly available datasets alongside structured engagement with institutional data custodians.

A comprehensive data governance framework, including roles, responsibilities, submission protocols, and approval processes, will be developed and documented in the Data Source and Collection Strategy Report.

## Identified Data Constraints

Preliminary review indicates the following constraints:

Limited availability of validated regional integration data

Gaps in nationally representative energy access quality data

Incomplete visibility on project-level implementation data

Variability in access to disaggregated financial and utility performance data

These constraints will be addressed through stakeholder engagement and data validation processes during implementation.

2022. SDG7 Tracking Report. World Bank / IEA / ESMAP

2025. Nigeria National Energy Compact. Federal Government of Nigeria.

2025. Third Quarter 2025 NERC Quarterly Report. Nigerian Electricity Regulatory Commission. Section 2.1.1 Available Generation Capacity.

2024. NDC Stocktake Report. Federal Government of Nigeria.

2020. MTF Nigeria Energy Access Diagnostic Report.